## PRESENTATION - INSTRUCTIONS
0 | GLF - ESMS | ENVIRONMENTAL AND SOCIAL MONITORING (ESMO) Tool | POWERED BY
| ESMO TOOL | PRESENTATION / INSTRUCTIONS
0 | INTRODUCTION | The Environmental and Social Monitoring (ESMO) tool is an Excel-based integrated tool used to monitor the implementation of the environmental and social management plan (ESMP) for projects funded by the GLF. This tool works alongside the Environmental and Social Screening and Assessment (ESSA) tool to manage the environmental and social aspects of GLF-funded projects throughout their development, approval, implementation, and closure phases. The ESMO tool is organized into the following sections, each in its own tab. If a project's ESMP includes more than five specific safeguard instruments, programs, or tools, the Grantee will add additional tabs (6.6, 6.7, 6.8, etc.). Each tab contains protected grey-shaded cells that cannot be modified, green-shaded cells intended for the Grantee to include specific information and blue-shaded cells reserved for GLF staff reviewing the tool. Each tab includes instructions presented in light green shaded boxes. The tabs transfer information between each other to prevent repetition and digitization errors. Each tab also includes instructions presented in light green shaded boxes.
1 | TAB 0: MASTER TAB | The Master tab contains the basic information for all the monitoring tabs. Grantees should fill it in using the information of their project’s ESMP. The Master tab has the following elements: • Project Number: Grantees must enter this number, which GLF will provide, in cell B2. • Project title: Grantees need to enter the project title in cell C3. • Name of the Grantee: Grantees must enter their name in cell C4. • Grant Duration: Grantees will use the drop-down menu in cell D4 to select the duration of their project in months (up to 36 months). • Grant Type: Grantees will use the drop-down menu in cell E4 to select the grant category from the following options: Small grant (up to $100,000) -- Medium grant (up to $250,000), or -- Large grant (over $250,000). • Grant E&S Category: Grantees will use the drop-down menu in cell F4 to select the E&S category of their project: (Category C or Category B), which was established by GLF. • Essential safeguard instruments and management tools: It contains five elements that are common to all projects: Compliance with Labour and Working Conditions Grievance Management Stakeholder Engagement Gender Accidents – Incidents – Reporting a. Grantees will use the drop-down menu in cells D9 to D13 to select the quarter in which each required action must be accomplished or ready to be operative. GLF has previously established these deadlines, which are included in the project’s ESMP. b. Grantees will write the name of the person responsible for the ESMP execution in cell F8. This name will be automatically repeated in cells F9 to F13. c. Grantees will use the drop-down menu in cells H9 to H13 to select the required actions' monitoring frequency. This information is included in the project’s ESMP. d. Grantees will use the drop-down menu in cells I9 to I13 and J9 to J13 to select the quarter when monitoring each of the required actions starts and ends. This information is included in the project’s ESMP. All this information will be reflected in the following monitoring tabs.
• Specific safeguard instruments, management programs and tools: It contains 11 E&S Safeguard Instruments, Management Programs, or Tools that might be required in a project’s ESMP. It is highly unlikely that an ESMP will contain all these elements but only some: Biodiversity Management Community - Occupational H&S Waste Management Hazardous Material Management Integrated Pest Management Emergency Response Process Framework Livelihood Restoration Security Management Plan Free, Prior, and Informed Consent (protocol) Human Rights Due Diligence Gender (the option "other" is included) a. Grantees will use the drop-down menu in cells D16 to D27 to select the quarter in which each required action must be accomplished or ready to be operative. GLF has previously established these deadlines, which are included in the project’s ESMP. b. Grantees will write the name of the person responsible for the ESMP execution in cell F15. This name will be automatically repeated in cells F16 to F27. c. Grantees will input in cells G16 to G27 the risks managed with each action. d. Grantees will use the drop-down menu in cells H16 to H27 to select the required actions' monitoring frequency. This information is included in the project’s ESMP. e. Grantees will use the drop-down menu in cells I16 to I27 and J16 to J27 to select the quarter when monitoring each of the required actions starts and ends. This information is included in the project’s ESMP. All this information will be reflected in the following monitoring tabs.
| MONITORING TABS TAB 1 - 5: MONITORING TABS ESMP - ESSENTIAL SAFEGUARDS AND INSTRUMENTS TABS 6.1 TO 6.5: SPECIFIC SAFEGUARDS AND INSTRUMENTS | The Monitoring Tabs consist of five tabs corresponding to the essential safeguard instruments and management tools (Tabs 1 to 5) that all projects need, and as many additional tabs as needed corresponding to the specific safeguard instrument, management program, or tools required for the specific projects. If the project does not need specific safeguards, Grantees will complete only Tabs 1 to 5. If the project needs some specific safeguards, Grantees should select the subject of the specific monitoring from a drop-down menu in cell C2, selecting one of the following options: • Biodiversity Management • Community - Occupational H&S • Waste Management • Hazardous Material Management • Integrated Pest Management • Emergency Response • Process Framework • Livelihood Restoration • Security Management Plan • Free, Prior, and Informed Consultation (protocol) • Human Rights Due Diligence Gender If the ESMP includes more than 5 of the abovementioned E&S Safeguard Instruments, Management Programs, or Tools, GLF will add the extra required tabs to the ESMO tool.
2 |  | The monitoring tabs contain the following elements: a. Report Number: Grantees should select the monitoring report number from a drop-down menu in cell E3, ranging from Report No. 1 to Report No. 12. b. Name of the person preparing the report: Grantees will fill in cell G2 with the name of the person preparing the monitoring report. c. Report Date: Grantees will fill cell H3 with the report completion date. d. Saving a report: Grantees can save the information they enter in the report by clicking the SAVE button in cell D4. e. Searching for a report: Grantees can search for a report by entering the report number in cell E2 and then clicking the SEARCH button in cell E4. f. Likelihood of the Risk: After completing all questions in column "C," Grantees will choose the likelihood of the risk from a drop-down menu in cell D5, selecting one of the following options (5 the more likely, 1 the less likely): 5. The risk is almost certainly going to materialize 4. The risk will almost surely materialize 3. The risk is likely to materialize 2. The risk may not materialize 1. The risk will almost surely not materialize g. Severity of the Risk: After completing all questions in column "C," Grantees will choose the severity of the risk from a drop-down menu in cell D6, selecting one of the following options (5 the more severe, 1 the less severe): 5. Large in magnitude or extent, significant, long-lasting or permanent, irreversible, may generate social conflict materialize 4. Of medium to large magnitude, affecting an extended area of territory, predictable, temporary and reversible 3. Location-specific, temporary, manageable, avoidable - or can be mitigated with known and feasible measures 2. Very limited, easily avoidable or manageable, affecting a very limited territory or population 1. Negligible, non-existent or minimal.
3 |  | h. Months of Project Execution: Grantees should select the number of months of project execution from a drop-down menu in cell H5, from 1 to 36 months. i. Scheduled action execution progress: Grantees should select the level of progress in executing the scheduled action from a drop-down menu in cell J5, selecting one of the following options: • According to the schedule • Slightly behind schedule • Severe delay • Other j. Indicative Questions: Column “C” contains the monitoring indicative questions. Grantees will answer those questions using the drop-down menu in cells D10 to D17 and follow the guidance of cells FG10 to FG17. Grantees will use the drop-down menu of cells H10 to H17 to establish the deadline for implementing the required action, selecting one of the following options: • Immediately • Over the next month • Over the next quarter • Over the next six months • When possible • Other Grantees will input the verification means of the required actions in cells K10 to K17. k. With this information, Grantees will finalize their monitoring report, and then they must SAVE their information by clicking the SAVE button in cell D4.
4 |  | l. The staff from GLF reviewing the monitoring tab will enter their name in cell M9. m. GLF Review: GLF staff will review each of the Grantee’s answers using the drop-down menu of cells I10 to I17, selecting one of the following options: • No objections • Objections – See comments (in which case they will write their comments in cells LM10 to LM17 and attach a comment sheet if more space is needed) • Other – See comments (same procedure as above) • No comments New Time Limit: If the review requires it, GLF staff will use the drop-down menu of cells J10 to J17 to set a new deadline for implementing the required action, selecting one of the following options: • Immediately • Over the next month • Over the next quarter • Over the next six months • When possible • Other • Same limit
6 | ESMO REPORT | The ESMO tool can generate consolidated E&S monitoring information in a graphical format for GLF reporting. These graphics can include ESMP safeguard instruments and tools and can be compared by grant category, Grantee, risk level, risk category, and other variables. The ESMO Report is reserved for GLF.

## 0. MASTER
ESMO Tool | GLF - ESMS | [7 empty] | POWERED BY
01-2025 | MASTER TAB |  |  | MONITORING INDEX
TITLE | Input the name of the Project | GRANT DURATION | GRANT TYPE | GRANT E&S CATEGORY
NAME OF GRANTEE | Input the name of the Grantee | 36 MONTHS | LARGE GRANT | CATEGORY B
01-2025 | ESSENTIAL SAFEGUARD INSTRUMENTS AND MANAGEMENT TOOLS | FROM WHEN MUST IT BE OPERATIONAL? | MONITORING SHEET NUMBER | RESPONSIBLE PERSON IN THE GRANTEE ORGANIZATION |  | FREQUENCY OF | DATES
| REQUIREMENT - ACTION |  |  | PABLO CORTEZ | RISK | PERFORMANCE MONITORING | STARTING | ENDING
| Compliance with Labour and Working Conditions | 2Q | 1 | PABLO CORTEZ | LABOUR AND WORKING CONDITIONS RISK | SEMIANNUAL | 2Q | CLOSURE
| Grievance Management | 2Q | 2 | PABLO CORTEZ | RISK OF INAPPROPRIATE HANDLING OF COMMUNITY OR WORKER GRIEVANCES | SEMIANNUAL | 2Q | CLOSURE
| Stakeholder Engagement | 3Q | 3 | PABLO CORTEZ | RISK OF LACK OF STAKEHOLDER CONSULTATION, PARTICIPATION AND CONSENT | QUARTERLY | 3Q | 10Q
| Gender | 2Q | 4 | PABLO CORTEZ | GENDER INEQUALITY RISK | SEMIANNUAL | 4Q | CLOSURE
| Accidents and Serious Incidents - Reporting | 2Q | 5 | PABLO CORTEZ |  | YEARLY | 4Q | CLOSURE
01-2025 | SPECIFIC SAFEGUARD INSTRUMENTS, MANAGEMENT PROGRAMS & TOOLS | FROM WHEN MUST IT BE OPERATIONAL? | MONITORING SHEET NUMBER | RESPONSIBLE PERSON IN THE GRANTEE ORGANIZATION |  | FREQUENCY OF | DATES
| REQUIREMENT - ACTION |  |  | PABLO CORTEZ | RISK | PERFORMANCE MONITORING | STARTING | ENDING
| Community - Occupational H&S | 4Q | 6.1 | PABLO CORTEZ | Community conditions and safety
| Process Framework | 7Q | 6.2 | PABLO CORTEZ | Livelihood loss | SEMIANNUAL | 8Q | 12Q
| Hazardous Material Management |  | 6.3 | PABLO CORTEZ | To be defined
| Emergency Response |  | 6.4 | PABLO CORTEZ | To be defined
|  |  | 6.5 | PABLO CORTEZ | To be defined
|  |  | 6.6 | PABLO CORTEZ | To be defined
|  |  | 6.7 | PABLO CORTEZ | To be defined
|  |  | 6.8 | PABLO CORTEZ | To be defined
|  |  | 6.9 | PABLO CORTEZ | To be defined
|  |  | 6.10 | PABLO CORTEZ | To be defined
|  |  | 6.11 | PABLO CORTEZ | To be defined
|  |  | 6.12 | PABLO CORTEZ | To be defined
INSTRUCTIONS
USE THE BLUE-SHADED CELLS IN COLUMN “G” TO INPUT THE RISK RELATED TO THE REQUIREMENT OR PLAN.

## 1. LABOUR
| ESMO Tool | GLF - ESMS - MONITORING TOOL | 1 |  | LABOUR AND WORKING CONDITIONS RISK | [7 empty] | POWERED BY
#REF! | 01-2025 | Compliance with Labour and Working Conditions |  | REPORT NUMBER | NAME OF THE PERSON PREPARING THIS REPORT | Another Reviewer | DATE OF THIS REPORT | GRANT CATEGORY | GRANT TYPE
| TITLE | Input the name of the Project | Once you have finish, save your work here | R-02- |  | FREQUENCY OF THIS PERFORMANCE MONITORING (AS INDICATED IN THE ESMP) | 2024-10-25 | CATEGORY B | LARGE GRANT
| NAME OF GRANTEE | Input the name of the Grantee | SAVE YOUR REPORT | SEARCH BY REPORT NUMBER | After this monitoring, the risk level has been assessed as indicated in the cell below | SEMIANNUAL | PREVIOUS MONITORING REPORT RISK LEVEL | LOW
|  | Likelihood of this risk: . | 3 |  | MEDIUM | NUMBER OF MONTHS OF PROJECT EXECUTION | 4 MONTHS | SCHEDULED ACTION PROGRESS | Slightly behind schedule
|  | Severity of this risk: . | 3 |  | INCREASED | PROJECT EXECUTION PERCENTAGE (TIME) | 11.11%
| 01-2025 | Compliance with Labour and Working Conditions |  |  | REQUIRED |  | TIME LIMIT FOR | GLF | NEW TIME LIMIT AFTER | VERIFICATION | GLF's COMMENTS (IF ANY) in columns "L" AND "M" | NAME OF GLF REVIEWER
|  | QUESTIONS |  |  | ACTIONS |  | IMPLEMENTING THE ACTION | REVIEW | GLF REVIEW | MEANS | Attach a comment sheet if more space is needed | ENTER THE NAME OF THE GLF REVIEWER
A | 1.1 | Is there a clear and transparent hiring process for project staff? | NO | SEE GUIDANCE | The grantee must ensure a clear and transparent hiring process to fulfill their Labor and Working Conditions. The risk level should be increased, and the grantee should implement this transparent process immediately. |  | When possible | OBJECTIONS - SEE COMMENTS | Immediately
B | 1.2 | Do the project employees have sufficient documentation about their working conditions and rights, including employment contracts, work schedules, salaries, overtime, compensation, and social or legal benefits? |  | SEE GUIDANCE | The grantee must provide adequate documentation to all staff and provide evidence of this action to GLF.
D | 1.3 | Does the project ensure that there is no discrimination based on sex, sexual orientation, age, ethnicity, disability, or any other factor and that work of equal value corresponds to equal pay? | YES | CONTINUE ANSWERING | The grantee must ensure equal remuneration for work of equal value, without discrimination. The risk level should be increased, and the grantee should implement this principle immediately. |  |  | NO OBJECTIONS
E | 1.4 | Is a functional Grievance Management Mechanism available for people working on the project? | NO | SEE GUIDANCE | A functional Grievance Management Mechanism available for project workers is part of the grantee’s commitment to Labour and Working Conditions. It should be put in place as soon as possible, and in the meantime, the risk level should be increased. |  | Over the next quarter | NO OBJECTIONS | Over the next quarter
F | 1.5 | Are the workers on the project at risk of occupational hazards? | NO | CONTINUE ANSWERING | If workers are exposed to occupational hazards, the grantee must develop an Occupational Health and Safety Plan. The risk level must be increased until this plan is implemented. |  |  | NO OBJECTIONS
G | 1.6 | Have there been cases of Sexual and Gender Violence (SGBV) among the people employed by the project during the period under monitoring? |  | SEE GUIDANCE | GLF is committed to preventing SGBV and mitigating its negative impacts. If the answer is YES, the grantee must report the actions taken and the outcome of this case. The risk level must be increased until preventive measures are fully implemented to avoid such cases in the future.
H | 1.7 | Does any aspect of the project execution contradict the Grantee's Statement of Compliance with Labour and Working Conditions? |  | SEE GUIDANCE | The grantee is responsible for ensuring that the Labor and Working Conditions outlined in the ESMP and grant agreement are met. The risk level must be raised until corrective measures are in place and these conditions are met.
I | 1.8 | Overall, is there a high risk of causing harm to communities or the environment with the activity or project that has been monitored? |  | SEE GUIDANCE | The grantee must take immediate action to prevent harm, increase the risk level, and report to GLF on the actions taken.
J
K
L
M
N
O
P
Q
R
S
T
U
SAVE
SEARCH
INSTRUCTIONS FOR GRANTEES (ATTACH A COMMENT SHEET IF MORE SPACE IS NEEDED - REFER TO THE QUESTION NUMBER)
ENTER YOUR NAME IN CELL G2.
ENTER COMPLETION DATE OF THIS REPORT IN CELL H3.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL H5 TO ENTER THE NUMBER OF MONTHS FOR PROJECT EXECUTION.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL J5 TO INPUT THE PROGRESS OF THE EXECUTION OF THE ACTION BEING MONITORED.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS D5 AND D6 TO ENTER THE SEVERITY AND LIKELIHOOD OF THE RISK.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL E3 TO ENTER THE MONITORING REPORT NUMBER.
IF YOU WANT TO CREATE A NEW REPORT, CHOOSE A NEW NUMBER AND THEN CLICK THE SAVE BUTTON BELOW .
IF YOU WANT TO CONSULT AN EXISTING REPORT, CHOOSE ITS NUMBER AND CLICK THE SEARCH BUTTON BELOW.
ANSWER THE
QUESTIONS ON
COLUMN "D" USING THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED OF COLUMN “H” TO SET A TIMELINE FOR IMPLEMENTING THE REQUIRED ACTION.
GLF REVIEWERS USE THE DROPDOWN MENU IN THE BLUE-SHADED COLUMN "I" TO INDICATE WHETHER THEY HAVE AN OBJECTION TO THE GRANTEE'S SELF-ASSESSMENT.
IF SO, PROPOSE A NEW TIMELINE FOR THE ACTION IMPLEMENTATION IN COLUMN "J" .
COLUMNS "I" AND "J"
COLUMN "H"
COLUMN "D"
INSTRUCTIONS FOR GLF REVIEWER
GRANTEES ENTER THE VERIFICATION MEANS IN THE BLUE-SHADED COLUMN “K”.
COLUMN "K"
COLUMNS "L" AND "M"
GLF REVIEWERS ENTER THEIR COMMENTS IN THE BLUE-SHADED COLUMN "L" AND “M”

## 2. GRIEVANCE MAN
| ESSE Tool | GLF - ESMS - MONITORING TOOL | 2 |  | RISK OF INAPPROPRIATE HANDLING OF COMMUNITY OR WORKER GRIEVANCES
#REF! | 01-2025 | Grievance Management |  | REPORT NUMBER | NAME OF THE PERSON PREPARING THIS REPORT | John Lenon | DATE OF THIS REPORT | GRANT CATEGORY | GRANT TYPE
| TITLE | Input the name of the Project | Once you have finish, save your work here | R-01- |  | FREQUENCY OF THIS PERFORMANCE MONITORING (AS INDICATED IN THE ESMP) | 2024-08-12 | CATEGORY B | LARGE GRANT
| NAME OF GRANTEE | Input the name of the Grantee |  | SEARCH BY REPORT NUMBER | After this monitoring, the risk level has been assessed as indicated in the cell below | SEMIANNUAL | PREVIOUS MONITORING REPORT RISK LEVEL
|  | Likelihood of this risk: . | 2 |  | MEDIUM | NUMBER OF MONTHS OF PROJECT EXECUTION | 12 MONTHS | SCHEDULED ACTION PROGRESS | Slightly behind schedule
|  | Severity of this risk: . | 3 |  |  | PROJECT EXECUTION PERCENTAGE (TIME) | 33.33%
| 01-2025 | Grievance Management |  |  | REQUIRED |  | TIME LIMIT FOR | GLF | NEW TIME LIMIT AFTER | VERIFICATION | GLF's COMMENTS (IF ANY) in columns "L" AND "M" | NAME OF GLF REVIEWER
|  | QUESTIONS |  |  | ACTIONS |  | IMPLEMENTING THE ACTION | REVIEW | GLF REVIEW | MEANS | Attach a comment sheet if more space is needed | ENTER THE NAME OF THE GLF REVIEWER
A | 2.1 | Is there a functional grievance mechanism available to the community? |  | SEE GUIDANCE | Projects must have a Grievance Mechanism compatible with the GLF's mechanism, available to communities and other stakeholders. If the mechanism is not functional, it must be operational by the end of next quarter at the latest.
B | 2.2 | Is there a functional grievance mechanism available for project employees |  | SEE GUIDANCE | Projects must have a Grievance Mechanism compatible with the GLF mechanism, available to project workers. If the mechanism is not functional, it must be operational by the end of next quarter at the latest.
C | 2.3 | Does the organization respond to or escalate complaints on time? |  | SEE GUIDANCE | If the answer is NO, increase the risk level. Grantees have two options for addressing a grievance: 1) A simple grievance can be addressed through the "Quick Response to Simple Grievances" process. 2) If the grievance is more complex and requires an investigation, it must be escalated to the GLF. Grantees must take prompt action to address either type of grievance.
D | 2.4 | How many complaints were received in the reporting period? |  | SEE GUIDANCE | If no complaints were received during the reporting period, it may be because the grievance management mechanism is not fully accessible. Grantees must ensure the accessibility and usability of their mechanisms. Conversely, a high number of complaints may indicate significant project problems that Grantees need to address.
F | 2.5 | Has the grievance management ever received any complaints? |  | SEE GUIDANCE | If the answer is NO, it could indicate that grievance management is not functioning properly. It may be inaccessible or not adequately disseminated among stakeholders. Grantees must review all aspects of their mechanisms.
G
H
I
J
K
L
M
N
O
P
Q
R
S
T
U
SAVE
SEARCH
INSTRUCTIONS FOR GRANTEES (ATTACH A COMMENT SHEET IF MORE SPACE IS NEEDED - REFER TO THE QUESTION NUMBER)
ENTER YOUR NAME IN CELL G2.
ENTER COMPLETION DATE OF THIS REPORT IN CELL H3.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL H5 TO ENTER THE NUMBER OF MONTHS FOR PROJECT EXECUTION.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL J5 TO INPUT THE PROGRESS OF THE EXECUTION OF THE ACTION BEING MONITORED.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS D5 AND D6 TO ENTER THE SEVERITY AND LIKELIHOOD OF THE RISK.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL E3 TO ENTER THE MONITORING REPORT NUMBER.
IF YOU WANT TO CREATE A NEW REPORT, CHOOSE A NEW NUMBER AND THEN CLICK THE SAVE BUTTON BELOW .
IF YOU WANT TO CONSULT AN EXISTING REPORT, CHOOSE ITS NUMBER AND CLICK THE SEARCH BUTTON BELOW.
ANSWER THE
QUESTIONS ON
COLUMN "D" USING THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED OF COLUMN “H” TO SET A TIMELINE FOR IMPLEMENTING THE REQUIRED ACTION.
GLF REVIEWERS USE THE DROPDOWN MENU IN THE BLUE-SHADED COLUMN "I" TO INDICATE WHETHER THEY HAVE AN OBJECTION TO THE GRANTEE'S SELF-ASSESSMENT.
IF SO, PROPOSE A NEW TIMELINE FOR THE ACTION IMPLEMENTATION IN COLUMN "J" .
COLUMNS "I" AND "J"
COLUMN "H"
COLUMN "D"
INSTRUCTIONS FOR GLF REVIEWER
GRANTEES ENTER THE VERIFICATION MEANS IN THE BLUE-SHADED COLUMN “K”.
COLUMN "K"
COLUMNS "L" AND "M"
GLF REVIEWERS ENTER THEIR COMMENTS IN THE BLUE-SHADED COLUMN "L" AND “M”

## 3. SEP
| ESSE Tool | GLF - ESMS - MONITORING TOOL | 3 |  | RISK OF LACK OF STAKEHOLDER CONSULTATION, PARTICIPATION AND CONSENT
#REF! | 01-2025 | Stakeholder Engagement |  | REPORT NUMBER | NAME OF THE PERSON PREPARING THIS REPORT | Louis Armstrong | DATE OF THIS REPORT | GRANT CATEGORY | GRANT TYPE
| TITLE | Input the name of the Project | Once you have finish, save your work here | R-02- |  | FREQUENCY OF THIS PERFORMANCE MONITORING (AS INDICATED IN THE ESMP) | 2024-11-22 | CATEGORY B | LARGE GRANT
| NAME OF GRANTEE | Input the name of the Grantee |  | SEARCH BY REPORT NUMBER | After this monitoring, the risk level has been assessed as indicated in the cell below | QUARTERLY | PREVIOUS MONITORING REPORT RISK LEVEL | LOW
|  | Likelihood of this risk: . | 5 |  | VERY HIGH | NUMBER OF MONTHS OF PROJECT EXECUTION | 5 MONTHS | SCHEDULED ACTION PROGRESS | Slightly behind schedule
|  | Severity of this risk: . | 5 |  | INCREASED | PROJECT EXECUTION PERCENTAGE (TIME) | 13.89%
| 01-2025 | Stakeholder Engagement |  |  | REQUIRED |  | TIME LIMIT FOR | GLF | NEW TIME LIMIT AFTER | VERIFICATION | GLF's COMMENTS (IF ANY) in columns "L" AND "M" | NAME OF GLF REVIEWER
|  | QUESTIONS |  |  | ACTIONS |  | IMPLEMENTING THE ACTION | REVIEW | GLF REVIEW | MEANS | Attach a comment sheet if more space is needed | ENTER THE NAME OF THE GLF REVIEWER
A | 3.1 | Does the project have a SEP? | NOT YET APPLICABLE | SEE GUIDANCE | All projects must have a Stakeholder Engagement Plan (SEP) formulated in accordance with the ESMP.
B | 3.2 | Is the grantee effectively engaging with project stakeholders? | YES | CONTINUE ANSWERING | Consider increasing the risk level. Effective stakeholder engagement is crucial for achieving project results and maintaining good environmental and social performance. Grantees must ensure ongoing engagement with project stakeholders.
D | 3.3 | Have the stakeholder engagement activities been conducted as scheduled during the period being monitored? | YES | CONTINUE ANSWERING | Consider increasing the risk level, unless there is a satisfactory explanation. Grantees should strive to carry out their stakeholder activities as planned unless there are emergent issues that require changes.
E | 3.4 | Are there any concerns raised by stakeholders that could significantly impact the project? | YES | SEE GUIDANCE | If stakeholders have serious concerns about the project, the Grantee should respond to these concerns and most likely advance concrete actions related to the concerns.
F | 3.5 | Is there equal participation between men and women in stakeholder activities, or is either group overrepresented to the detriment of the other? | NO | SEE GUIDANCE | The Grantee must make a significant effort to ensure equitable participation unless there is a clear reason for a substantial difference in participation between the two groups.
G | 3.6 | Is the Grantee correctly documenting stakeholder engagement activities? | NO | SEE GUIDANCE | The Grantee must accurately record stakeholder involvement activities using various media, such as written, audiovisual, or other forms of media.
H
I
J
K
L
M
N
O
P
Q
R
S
T
U
SAVE
SEARCH
INSTRUCTIONS FOR GRANTEES (ATTACH A COMMENT SHEET IF MORE SPACE IS NEEDED - REFER TO THE QUESTION NUMBER)
ENTER YOUR NAME IN CELL G2.
ENTER COMPLETION DATE OF THIS REPORT IN CELL H3.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL H5 TO ENTER THE NUMBER OF MONTHS FOR PROJECT EXECUTION.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL J5 TO INPUT THE PROGRESS OF THE EXECUTION OF THE ACTION BEING MONITORED.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS D5 AND D6 TO ENTER THE SEVERITY AND LIKELIHOOD OF THE RISK.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL E3 TO ENTER THE MONITORING REPORT NUMBER.
IF YOU WANT TO CREATE A NEW REPORT, CHOOSE A NEW NUMBER AND THEN CLICK THE SAVE BUTTON BELOW .
IF YOU WANT TO CONSULT AN EXISTING REPORT, CHOOSE ITS NUMBER AND CLICK THE SEARCH BUTTON BELOW.
ANSWER THE
QUESTIONS ON
COLUMN "D" USING THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED OF COLUMN “H” TO SET A TIMELINE FOR IMPLEMENTING THE REQUIRED ACTION.
GLF REVIEWERS USE THE DROPDOWN MENU IN THE BLUE-SHADED COLUMN "I" TO INDICATE WHETHER THEY HAVE AN OBJECTION TO THE GRANTEE'S SELF-ASSESSMENT.
IF SO, PROPOSE A NEW TIMELINE FOR THE ACTION IMPLEMENTATION IN COLUMN "J" .
COLUMNS "I" AND "J"
COLUMN "H"
COLUMN "D"
INSTRUCTIONS FOR GLF REVIEWER
GRANTEES ENTER THE VERIFICATION MEANS IN THE BLUE-SHADED COLUMN “K”.
COLUMN "K"
COLUMNS "L" AND "M"
GLF REVIEWERS ENTER THEIR COMMENTS IN THE BLUE-SHADED COLUMN "L" AND “M”

## 4. GENDER
| ESSE Tool | GLF - ESMS - MONITORING TOOL | 4 |  | GENDER INEQUALITY RISK
#REF! | 01-2025 | Gender |  | REPORT NUMBER | NAME OF THE PERSON PREPARING THIS REPORT | R. Bolaño | DATE OF THIS REPORT | GRANT CATEGORY | GRANT TYPE
| TITLE | Input the name of the Project | Once you have finish, save your work here | R-04- |  | FREQUENCY OF THIS PERFORMANCE MONITORING (AS INDICATED IN THE ESMP) | 2024-02-20 | CATEGORY B | LARGE GRANT
| NAME OF GRANTEE | Input the name of the Grantee |  | SEARCH BY REPORT NUMBER | After this monitoring, the risk level has been assessed as indicated in the cell below | YEARLY | PREVIOUS MONITORING REPORT RISK LEVEL | LOW
|  | Likelihood of this risk: . | 4 |  | VERY HIGH | NUMBER OF MONTHS OF PROJECT EXECUTION | 6 MONTHS | SCHEDULED ACTION PROGRESS | Earlier than the schedule
|  | Severity of this risk: . | 4 |  | INCREASED | PROJECT EXECUTION PERCENTAGE (TIME) | 16.67%
| 01-2025 | Gender |  |  | REQUIRED |  | TIME LIMIT FOR | GLF | NEW TIME LIMIT AFTER | VERIFICATION | GLF's COMMENTS (IF ANY) in columns "L" AND "M" | NAME OF GLF REVIEWER
|  | QUESTIONS |  |  | ACTIONS |  | IMPLEMENTING THE ACTION | REVIEW | GLF REVIEW | MEANS | Attach a comment sheet if more space is needed | ENTER THE NAME OF THE GLF REVIEWER
A | 4.1 | Is the project taking into account relevant gender issues and concerns? | YES | CONTINUE ANSWERING |  |  | Over the next quarter | NO OBJECTIONS | Over the next quarter
B | 4.2 | Are the project indicators, milestones, and targets inclusive of gender considerations? | YES | CONTINUE ANSWERING |  |  | Over the next six months | OBJECTIONS - SEE COMMENTS | Over the next quarter
C | 4.3 | Does the project collect sex-disaggregated data? | NOT YET APPLICABLE | SEE GUIDANCE |  |  | Over the next six months | NO OBJECTIONS | Over the next six months
D | 4.4 | Are the project activities conflicting with the GLF's gender equality plan in any way? | NO | CONTINUE ANSWERING |  |  | Over the next month | OBJECTIONS - SEE COMMENTS | Immediately
E | 4.5 | Has there been any case of gender-based violence reported during this period? | NO | CONTINUE ANSWERING
F | 4.6 | Does the project progress report include the intervention's impact on women, men, and gender relations? | YES | END THE MONITORING
G
H
I
J
K
L
M
N
O
P
Q
R
SAVE
SEARCH
INSTRUCTIONS FOR GRANTEES (ATTACH A COMMENT SHEET IF MORE SPACE IS NEEDED - REFER TO THE QUESTION NUMBER)
ENTER YOUR NAME IN CELL G2.
ENTER COMPLETION DATE OF THIS REPORT IN CELL H3.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL H5 TO ENTER THE NUMBER OF MONTHS FOR PROJECT EXECUTION.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL J5 TO INPUT THE PROGRESS OF THE EXECUTION OF THE ACTION BEING MONITORED.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS D5 AND D6 TO ENTER THE SEVERITY AND LIKELIHOOD OF THE RISK.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL E3 TO ENTER THE MONITORING REPORT NUMBER.
IF YOU WANT TO CREATE A NEW REPORT, CHOOSE A NEW NUMBER AND THEN CLICK THE SAVE BUTTON BELOW .
IF YOU WANT TO CONSULT AN EXISTING REPORT, CHOOSE ITS NUMBER AND CLICK THE SEARCH BUTTON BELOW.
ANSWER THE
QUESTIONS ON
COLUMN "D" USING THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED OF COLUMN “H” TO SET A TIMELINE FOR IMPLEMENTING THE REQUIRED ACTION.
GLF REVIEWERS USE THE DROPDOWN MENU IN THE BLUE-SHADED COLUMN "I" TO INDICATE WHETHER THEY HAVE AN OBJECTION TO THE GRANTEE'S SELF-ASSESSMENT.
IF SO, PROPOSE A NEW TIMELINE FOR THE ACTION IMPLEMENTATION IN COLUMN "J" .
COLUMNS "I" AND "J"
COLUMN "H"
COLUMN "D"
INSTRUCTIONS FOR GLF REVIEWER
GRANTEES ENTER THE VERIFICATION MEANS IN THE BLUE-SHADED COLUMN “K”.
COLUMN "K"
COLUMNS "L" AND "M"
GLF REVIEWERS ENTER THEIR COMMENTS IN THE BLUE-SHADED COLUMN "L" AND “M”

## 5. ACCIDENTS-INCIDENTS
| ESSE Tool | GLF - ESMS - MONITORING TOOL | 5 |  | 0
#REF! | 01-2025 | Accidents and Serious Incidents - Reporting |  | REPORT NUMBER | NAME OF THE PERSON PREPARING THIS REPORT | Louis Armstrong | DATE OF THIS REPORT | GRANT CATEGORY | GRANT TYPE
| TITLE | Input the name of the Project | Once you have finish, save your work here | R-02- |  | FREQUENCY OF THIS PERFORMANCE MONITORING (AS INDICATED IN THE ESMP) | 2024-11-22 | CATEGORY B | LARGE GRANT
| NAME OF GRANTEE | Input the name of the Grantee |  | SEARCH BY REPORT NUMBER | After this monitoring, the risk level has been assessed as indicated in the cell below | QUARTERLY | PREVIOUS MONITORING REPORT RISK LEVEL | LOW
|  | Likelihood of this risk: . | 3 |  | MEDIUM | NUMBER OF MONTHS OF PROJECT EXECUTION | 5 MONTHS | SCHEDULED ACTION PROGRESS | Slightly behind schedule
|  | Severity of this risk: . | 2 |  | INCREASED | PROJECT EXECUTION PERCENTAGE (TIME) | 13.89%
| 01-2025 | Accidents and Serious Incidents - Reporting |  |  | REQUIRED |  | TIME LIMIT FOR | GLF | NEW TIME LIMIT AFTER | VERIFICATION | GLF's COMMENTS (IF ANY) in columns "L" AND "M" | NAME OF GLF REVIEWER
|  | QUESTIONS |  |  | ACTIONS |  | IMPLEMENTING THE ACTION | REVIEW | GLF REVIEW | MEANS | Attach a comment sheet if more space is needed | ENTER THE NAME OF THE GLF REVIEWER
A | 5.1 | Has the Grantee reported any incidents or accidents on the project during the reporting period? |  | GO TO QUESTION 5.7
B | 5.2 | Has the Grantee reported the incident or accident to the relevant authorities in Galapagos? |  | SEE GUIDANCE | GLF requires Grantees to promptly report any event, incident or accident related to environmental, occupational health and safety, public health and safety, or social issues occurring in the project area that may have a significant adverse impact, attract negative external attention, or give rise to potential liability. If there is no explanation for the lack of a report, raise the risk level.
C | 5.3 | Was the incident or accident report filed using the GLF reporting tool? |  | SEE GUIDANCE | The Grantee must report to GLF and to the appropriate regulatory agency on community and occupational health and safety matters in a manner that satisfies Ecuadorian legislation and the requirements set by following the EHS Guideline (2.0). The Grantee should use the the Occupational Accident / Incident Reporting Form of the GLF or a similar format.
D | 5.4 | Has the incident or accident been investigated by someone who is knowledgeable and competent in occupational safety? |  | SEE GUIDANCE | All reported occupational accidents, diseases, dangerous occurrences, incidents, and near misses should be investigated by someone knowledgeable/competent in occupational safety. If the investigation has not been carried out without an acceptable reason, then the project's risk level should be increased.
E | 5.5 | Have the root causes of the incident or accident been determined? |  | SEE GUIDANCE | Investigations must identify the underlying causes of an incident or accident. If the investigation fails to do so, the project's risk level should be increased until the root cause is established.
F | 5.6 | Has the Grantee implemented any preventive measures or improved processes as a result of the investigation? |  | SEE GUIDANCE | If the investigation has been completed and the root causes have been identified, the Grantee must take appropriate measures to prevent these accidents or incidents from happening again. Increase the project’s risk level until preventive measures are in place.
G | 5.7 | Has the Grantee established processes and systems to report and record work-related accidents, diseases, dangerous occurrences, and incidents? |  | SEE GUIDANCE
H
I
J
K
L
M
N
O
P
Q
R
S
T
U
SAVE
SEARCH
INSTRUCTIONS FOR GRANTEES (ATTACH A COMMENT SHEET IF MORE SPACE IS NEEDED - REFER TO THE QUESTION NUMBER)
ENTER YOUR NAME IN CELL G2.
ENTER COMPLETION DATE OF THIS REPORT IN CELL H3.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL H5 TO ENTER THE NUMBER OF MONTHS FOR PROJECT EXECUTION.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL J5 TO INPUT THE PROGRESS OF THE EXECUTION OF THE ACTION BEING MONITORED.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS D5 AND D6 TO ENTER THE SEVERITY AND LIKELIHOOD OF THE RISK.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL E3 TO ENTER THE MONITORING REPORT NUMBER.
IF YOU WANT TO CREATE A NEW REPORT, CHOOSE A NEW NUMBER AND THEN CLICK THE SAVE BUTTON BELOW .
IF YOU WANT TO CONSULT AN EXISTING REPORT, CHOOSE ITS NUMBER AND CLICK THE SEARCH BUTTON BELOW.
ANSWER THE
QUESTIONS ON
COLUMN "D" USING THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED OF COLUMN “H” TO SET A TIMELINE FOR IMPLEMENTING THE REQUIRED ACTION.
GLF REVIEWERS USE THE DROPDOWN MENU IN THE BLUE-SHADED COLUMN "I" TO INDICATE WHETHER THEY HAVE AN OBJECTION TO THE GRANTEE'S SELF-ASSESSMENT.
IF SO, PROPOSE A NEW TIMELINE FOR THE ACTION IMPLEMENTATION IN COLUMN "J" .
COLUMNS "I" AND "J"
COLUMN "H"
COLUMN "D"
INSTRUCTIONS FOR GLF REVIEWER
GRANTEES ENTER THE VERIFICATION MEANS IN THE BLUE-SHADED COLUMN “K”.
COLUMN "K"
COLUMNS "L" AND "M"
GLF REVIEWERS ENTER THEIR COMMENTS IN THE BLUE-SHADED COLUMN "L" AND “M”

## 6.1.SPC-ESMP
| ESSE Tool | GLF - ESMS - MONITORING TOOL | 4 |  | Community conditions and safety
#REF! | 01-2025 |  |  | REPORT NUMBER | NAME OF THE PERSON PREPARING THIS REPORT | PABLO CORTEZ | DATE OF THIS REPORT | GRANT CATEGORY | GRANT TYPE
| TITLE | Input the name of the Project | Once you have finish, save your work here | R-01- |  | FREQUENCY OF THIS PERFORMANCE MONITORING (AS INDICATED IN THE ESMP) | 2024-08-20 | CATEGORY B | LARGE GRANT
| NAME OF GRANTEE | Input the name of the Grantee |  | SEARCH BY REPORT NUMBER | After this monitoring, the risk level has been assessed as indicated in the cell below | YEARLY | PREVIOUS MONITORING REPORT RISK LEVEL
|  | Likelihood of this risk: . | 1 |  | LOW | NUMBER OF MONTHS OF PROJECT EXECUTION | 6 MONTHS | SCHEDULED ACTION PROGRESS | According to the schedule
|  | Severity of this risk: . | 1 |  | DECREASED | PROJECT EXECUTION PERCENTAGE (TIME) | 16.67%
| 01-2025 | 0 |  |  | REQUIRED |  | TIME LIMIT FOR | GLF | NEW TIME LIMIT AFTER | VERIFICATION | GLF's COMMENTS (IF ANY) in columns "L" AND "M" | NAME OF GLF REVIEWER
|  | QUESTIONS |  |  | ACTIONS |  | IMPLEMENTING THE ACTION | REVIEW | GLF REVIEW | MEANS | Attach a comment sheet if more space is needed | ENTER THE NAME OF THE GLF REVIEWER
A | 6.1.1 |  |  | SEE GUIDANCE
B | 6.1.2 |  |  | SEE GUIDANCE
C | 6.1.3 |  |  | SEE GUIDANCE
D | 6.1.4 |  |  | SEE GUIDANCE
E | 6.1.5 |  |  | SEE GUIDANCE
F
G
H
I
J
K
L
P
Q
R
S
T
SAVE
SEARCH
INSTRUCTIONS FOR GRANTEES (ATTACH A COMMENT SHEET IF MORE SPACE IS NEEDED - REFER TO THE QUESTION NUMBER)
ENTER YOUR NAME IN CELL G2.
ENTER COMPLETION DATE OF THIS REPORT IN CELL H3.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL H5 TO ENTER THE NUMBER OF MONTHS FOR PROJECT EXECUTION.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL J5 TO INPUT THE PROGRESS OF THE EXECUTION OF THE ACTION BEING MONITORED.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS D5 AND D6 TO ENTER THE SEVERITY AND LIKELIHOOD OF THE RISK.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL E3 TO ENTER THE MONITORING REPORT NUMBER.
IF YOU WANT TO CREATE A NEW REPORT, CHOOSE A NEW NUMBER AND THEN CLICK THE SAVE BUTTON BELOW .
IF YOU WANT TO CONSULT AN EXISTING REPORT, CHOOSE ITS NUMBER AND CLICK THE SEARCH BUTTON BELOW.
ANSWER THE
QUESTIONS ON
COLUMN "D" USING THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED OF COLUMN “H” TO SET A TIMELINE FOR IMPLEMENTING THE REQUIRED ACTION.
GLF REVIEWERS USE THE DROPDOWN MENU IN THE BLUE-SHADED COLUMN "I" TO INDICATE WHETHER THEY HAVE AN OBJECTION TO THE GRANTEE'S SELF-ASSESSMENT.
IF SO, PROPOSE A NEW TIMELINE FOR THE ACTION IMPLEMENTATION IN COLUMN "J" .
COLUMNS "I" AND "J"
COLUMN "H"
COLUMN "D"
INSTRUCTIONS FOR GLF REVIEWER
GRANTEES ENTER THE VERIFICATION MEANS IN THE BLUE-SHADED COLUMN “K”.
COLUMN "K"
COLUMNS "L" AND "M"
GLF REVIEWERS ENTER THEIR COMMENTS IN THE BLUE-SHADED COLUMN "L" AND “M”

## 6.2.SPC-ESMP
| ESSE Tool | GLF - ESMS - MONITORING TOOL | 4 |  | Livelihood loss
#REF! | 01-2025 |  |  | REPORT NUMBER | NAME OF THE PERSON PREPARING THIS REPORT | R. Bolaño | DATE OF THIS REPORT | GRANT CATEGORY | GRANT TYPE
| TITLE | Input the name of the Project | Once you have finish, save your work here | R-06- |  | FREQUENCY OF THIS PERFORMANCE MONITORING (AS INDICATED IN THE ESMP) | 2024-02-20 | CATEGORY B | LARGE GRANT
| NAME OF GRANTEE | Input the name of the Grantee |  | SEARCH BY REPORT NUMBER | After this monitoring, the risk level has been assessed as indicated in the cell below | YEARLY | PREVIOUS MONITORING REPORT RISK LEVEL | LOW
|  | Likelihood of this risk: . | 1 |  | LOW | NUMBER OF MONTHS OF PROJECT EXECUTION | 21 MONTHS | SCHEDULED ACTION PROGRESS | Earlier than the schedule
|  | Severity of this risk: . | 1 |  | DECREASED | PROJECT EXECUTION PERCENTAGE (TIME) | 58.33%
| 01-2025 | 0 |  |  | REQUIRED |  | TIME LIMIT FOR | GLF | NEW TIME LIMIT AFTER | VERIFICATION | GLF's COMMENTS (IF ANY) in columns "L" AND "M" | NAME OF GLF REVIEWER
|  | QUESTIONS |  |  | ACTIONS |  | IMPLEMENTING THE ACTION | REVIEW | GLF REVIEW | MEANS | Attach a comment sheet if more space is needed | ENTER THE NAME OF THE GLF REVIEWER
A | 6.2.1 |  | YES | CONTINUE ANSWERING
B | 6.2.2 |  | YES | CONTINUE ANSWERING
C | 6.2.3 |  | YES | CONTINUE ANSWERING
D | 6.2.4 |  | NO | CONTINUE ANSWERING
E | 6.2.5 |  | YES | END THE MONITORING
F
G
H
I
J
K
L
P
Q
R
S
T
SAVE
SEARCH
INSTRUCTIONS FOR GRANTEES (ATTACH A COMMENT SHEET IF MORE SPACE IS NEEDED - REFER TO THE QUESTION NUMBER)
ENTER YOUR NAME IN CELL G2.
ENTER COMPLETION DATE OF THIS REPORT IN CELL H3.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL H5 TO ENTER THE NUMBER OF MONTHS FOR PROJECT EXECUTION.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL J5 TO INPUT THE PROGRESS OF THE EXECUTION OF THE ACTION BEING MONITORED.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS D5 AND D6 TO ENTER THE SEVERITY AND LIKELIHOOD OF THE RISK.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL E3 TO ENTER THE MONITORING REPORT NUMBER.
IF YOU WANT TO CREATE A NEW REPORT, CHOOSE A NEW NUMBER AND THEN CLICK THE SAVE BUTTON BELOW .
IF YOU WANT TO CONSULT AN EXISTING REPORT, CHOOSE ITS NUMBER AND CLICK THE SEARCH BUTTON BELOW.
ANSWER THE
QUESTIONS ON
COLUMN "D" USING THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED OF COLUMN “H” TO SET A TIMELINE FOR IMPLEMENTING THE REQUIRED ACTION.
GLF REVIEWERS USE THE DROPDOWN MENU IN THE BLUE-SHADED COLUMN "I" TO INDICATE WHETHER THEY HAVE AN OBJECTION TO THE GRANTEE'S SELF-ASSESSMENT.
IF SO, PROPOSE A NEW TIMELINE FOR THE ACTION IMPLEMENTATION IN COLUMN "J" .
COLUMNS "I" AND "J"
COLUMN "H"
COLUMN "D"
INSTRUCTIONS FOR GLF REVIEWER
GRANTEES ENTER THE VERIFICATION MEANS IN THE BLUE-SHADED COLUMN “K”.
COLUMN "K"
COLUMNS "L" AND "M"
GLF REVIEWERS ENTER THEIR COMMENTS IN THE BLUE-SHADED COLUMN "L" AND “M”

## 6.3.SPC-ESMP
| ESSE Tool | GLF - ESMS - MONITORING TOOL | 4 |  | To be defined
#REF! | 01-2025 |  |  | REPORT NUMBER | NAME OF THE PERSON PREPARING THIS REPORT | R. Bolaño | DATE OF THIS REPORT | GRANT CATEGORY | GRANT TYPE
| TITLE | Input the name of the Project | Once you have finish, save your work here | R-06- |  | FREQUENCY OF THIS PERFORMANCE MONITORING (AS INDICATED IN THE ESMP) | 2024-02-20 | CATEGORY B | LARGE GRANT
| NAME OF GRANTEE | Input the name of the Grantee |  | SEARCH BY REPORT NUMBER | After this monitoring, the risk level has been assessed as indicated in the cell below | YEARLY | PREVIOUS MONITORING REPORT RISK LEVEL | LOW
|  | Likelihood of this risk: . | 1 |  | LOW | NUMBER OF MONTHS OF PROJECT EXECUTION | 21 MONTHS | SCHEDULED ACTION PROGRESS | Earlier than the schedule
|  | Severity of this risk: . | 1 |  | DECREASED | PROJECT EXECUTION PERCENTAGE (TIME) | 58.33%
| 01-2025 | 0 |  |  | REQUIRED |  | TIME LIMIT FOR | GLF | NEW TIME LIMIT AFTER | VERIFICATION | GLF's COMMENTS (IF ANY) in columns "L" AND "M" | NAME OF GLF REVIEWER
|  | QUESTIONS |  |  | ACTIONS |  | IMPLEMENTING THE ACTION | REVIEW | GLF REVIEW | MEANS | Attach a comment sheet if more space is needed | ENTER THE NAME OF THE GLF REVIEWER
A | 6.3.1 |  | YES | CONTINUE ANSWERING
B | 6.3.2 |  | YES | CONTINUE ANSWERING
C | 6.3.3 |  | YES | CONTINUE ANSWERING
D | 6.3.4 |  | NO | CONTINUE ANSWERING
E | 6.3.5 |  | YES | END THE MONITORING
F
G
H
I
J
K
L
P
Q
R
S
T
SAVE
SEARCH
INSTRUCTIONS FOR GRANTEES (ATTACH A COMMENT SHEET IF MORE SPACE IS NEEDED - REFER TO THE QUESTION NUMBER)
ENTER YOUR NAME IN CELL G2.
ENTER COMPLETION DATE OF THIS REPORT IN CELL H3.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL H5 TO ENTER THE NUMBER OF MONTHS FOR PROJECT EXECUTION.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL J5 TO INPUT THE PROGRESS OF THE EXECUTION OF THE ACTION BEING MONITORED.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS D5 AND D6 TO ENTER THE SEVERITY AND LIKELIHOOD OF THE RISK.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL E3 TO ENTER THE MONITORING REPORT NUMBER.
IF YOU WANT TO CREATE A NEW REPORT, CHOOSE A NEW NUMBER AND THEN CLICK THE SAVE BUTTON BELOW .
IF YOU WANT TO CONSULT AN EXISTING REPORT, CHOOSE ITS NUMBER AND CLICK THE SEARCH BUTTON BELOW.
ANSWER THE
QUESTIONS ON
COLUMN "D" USING THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED OF COLUMN “H” TO SET A TIMELINE FOR IMPLEMENTING THE REQUIRED ACTION.
GLF REVIEWERS USE THE DROPDOWN MENU IN THE BLUE-SHADED COLUMN "I" TO INDICATE WHETHER THEY HAVE AN OBJECTION TO THE GRANTEE'S SELF-ASSESSMENT.
IF SO, PROPOSE A NEW TIMELINE FOR THE ACTION IMPLEMENTATION IN COLUMN "J" .
COLUMNS "I" AND "J"
COLUMN "H"
COLUMN "D"
INSTRUCTIONS FOR GLF REVIEWER
GRANTEES ENTER THE VERIFICATION MEANS IN THE BLUE-SHADED COLUMN “K”.
COLUMN "K"
COLUMNS "L" AND "M"
GLF REVIEWERS ENTER THEIR COMMENTS IN THE BLUE-SHADED COLUMN "L" AND “M”

## 6.4.SPC-ESMP
| ESSE Tool | GLF - ESMS - MONITORING TOOL | 4 |  | To be defined
#REF! | 01-2025 |  |  | REPORT NUMBER | NAME OF THE PERSON PREPARING THIS REPORT | R. Bolaño | DATE OF THIS REPORT | GRANT CATEGORY | GRANT TYPE
| TITLE | Input the name of the Project | Once you have finish, save your work here | R-06- |  | FREQUENCY OF THIS PERFORMANCE MONITORING (AS INDICATED IN THE ESMP) | 2024-02-20 | CATEGORY B | LARGE GRANT
| NAME OF GRANTEE | Input the name of the Grantee |  | SEARCH BY REPORT NUMBER | After this monitoring, the risk level has been assessed as indicated in the cell below | YEARLY | PREVIOUS MONITORING REPORT RISK LEVEL | LOW
|  | Likelihood of this risk: . | 1 |  | LOW | NUMBER OF MONTHS OF PROJECT EXECUTION | 21 MONTHS | SCHEDULED ACTION PROGRESS | Earlier than the schedule
|  | Severity of this risk: . | 1 |  | DECREASED | PROJECT EXECUTION PERCENTAGE (TIME) | 58.33%
| 01-2025 | 0 |  |  | REQUIRED |  | TIME LIMIT FOR | GLF | NEW TIME LIMIT AFTER | VERIFICATION | GLF's COMMENTS (IF ANY) in columns "L" AND "M" | NAME OF GLF REVIEWER
|  | QUESTIONS |  |  | ACTIONS |  | IMPLEMENTING THE ACTION | REVIEW | GLF REVIEW | MEANS | Attach a comment sheet if more space is needed | ENTER THE NAME OF THE GLF REVIEWER
A | 6.4.1 |  | YES | CONTINUE ANSWERING
B | 6.4.2 |  | YES | CONTINUE ANSWERING
C | 6.4.3 |  | YES | CONTINUE ANSWERING
D | 6.4.4 |  | NO | CONTINUE ANSWERING
E | 6.4.5 |  | YES | END THE MONITORING
F
G
H
I
J
K
L
P
Q
R
S
T
SAVE
SEARCH
INSTRUCTIONS FOR GRANTEES (ATTACH A COMMENT SHEET IF MORE SPACE IS NEEDED - REFER TO THE QUESTION NUMBER)
ENTER YOUR NAME IN CELL G2.
ENTER COMPLETION DATE OF THIS REPORT IN CELL H3.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL H5 TO ENTER THE NUMBER OF MONTHS FOR PROJECT EXECUTION.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL J5 TO INPUT THE PROGRESS OF THE EXECUTION OF THE ACTION BEING MONITORED.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS D5 AND D6 TO ENTER THE SEVERITY AND LIKELIHOOD OF THE RISK.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL E3 TO ENTER THE MONITORING REPORT NUMBER.
IF YOU WANT TO CREATE A NEW REPORT, CHOOSE A NEW NUMBER AND THEN CLICK THE SAVE BUTTON BELOW .
IF YOU WANT TO CONSULT AN EXISTING REPORT, CHOOSE ITS NUMBER AND CLICK THE SEARCH BUTTON BELOW.
ANSWER THE
QUESTIONS ON
COLUMN "D" USING THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED OF COLUMN “H” TO SET A TIMELINE FOR IMPLEMENTING THE REQUIRED ACTION.
GLF REVIEWERS USE THE DROPDOWN MENU IN THE BLUE-SHADED COLUMN "I" TO INDICATE WHETHER THEY HAVE AN OBJECTION TO THE GRANTEE'S SELF-ASSESSMENT.
IF SO, PROPOSE A NEW TIMELINE FOR THE ACTION IMPLEMENTATION IN COLUMN "J" .
COLUMNS "I" AND "J"
COLUMN "H"
COLUMN "D"
INSTRUCTIONS FOR GLF REVIEWER
GRANTEES ENTER THE VERIFICATION MEANS IN THE BLUE-SHADED COLUMN “K”.
COLUMN "K"
COLUMNS "L" AND "M"
GLF REVIEWERS ENTER THEIR COMMENTS IN THE BLUE-SHADED COLUMN "L" AND “M”

## 6.5.SPC-ESMP
| ESSE Tool | GLF - ESMS - MONITORING TOOL | 4 |  | To be defined
#REF! | 01-2025 |  |  | REPORT NUMBER | NAME OF THE PERSON PREPARING THIS REPORT | R. Bolaño | DATE OF THIS REPORT | GRANT CATEGORY | GRANT TYPE
| TITLE | Input the name of the Project | Once you have finish, save your work here | R-03- |  | FREQUENCY OF THIS PERFORMANCE MONITORING (AS INDICATED IN THE ESMP) | 2024-02-20 | CATEGORY B | LARGE GRANT
| NAME OF GRANTEE | Input the name of the Grantee |  | SEARCH BY REPORT NUMBER | After this monitoring, the risk level has been assessed as indicated in the cell below | YEARLY | PREVIOUS MONITORING REPORT RISK LEVEL | LOW
|  | Likelihood of this risk: . | 3 |  | MEDIUM | NUMBER OF MONTHS OF PROJECT EXECUTION | 9 MONTHS | SCHEDULED ACTION PROGRESS | Earlier than the schedule
|  | Severity of this risk: . | 3 |  | INCREASED | PROJECT EXECUTION PERCENTAGE (TIME) | 25%
| 01-2025 | 0 |  |  | REQUIRED |  | TIME LIMIT FOR | GLF | NEW TIME LIMIT AFTER | VERIFICATION | GLF's COMMENTS (IF ANY) in columns "L" AND "M" | NAME OF GLF REVIEWER
|  | QUESTIONS |  |  | ACTIONS |  | IMPLEMENTING THE ACTION | REVIEW | GLF REVIEW | MEANS | Attach a comment sheet if more space is needed | ENTER THE NAME OF THE GLF REVIEWER
A | 6.5.1 |  |  | SEE GUIDANCE
B | 6.5.2 |  | YES | CONTINUE ANSWERING
C | 6.5.3 |  | YES | CONTINUE ANSWERING
D | 6.5.4 |  | NO | CONTINUE ANSWERING
E | 6.5.5 |  | YES | END THE MONITORING
F
G
H
I
J
K
L
P
Q
R
S
T
SAVE
SEARCH
INSTRUCTIONS FOR GRANTEES (ATTACH A COMMENT SHEET IF MORE SPACE IS NEEDED - REFER TO THE QUESTION NUMBER)
ENTER YOUR NAME IN CELL G2.
ENTER COMPLETION DATE OF THIS REPORT IN CELL H3.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL H5 TO ENTER THE NUMBER OF MONTHS FOR PROJECT EXECUTION.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL J5 TO INPUT THE PROGRESS OF THE EXECUTION OF THE ACTION BEING MONITORED.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS D5 AND D6 TO ENTER THE SEVERITY AND LIKELIHOOD OF THE RISK.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED CELL E3 TO ENTER THE MONITORING REPORT NUMBER.
IF YOU WANT TO CREATE A NEW REPORT, CHOOSE A NEW NUMBER AND THEN CLICK THE SAVE BUTTON BELOW .
IF YOU WANT TO CONSULT AN EXISTING REPORT, CHOOSE ITS NUMBER AND CLICK THE SEARCH BUTTON BELOW.
ANSWER THE
QUESTIONS ON
COLUMN "D" USING THE DROP-DOWN MENU IN THE BLUE-SHADED CELLS.
USE THE DROP-DOWN MENU IN THE BLUE-SHADED OF COLUMN “H” TO SET A TIMELINE FOR IMPLEMENTING THE REQUIRED ACTION.
GLF REVIEWERS USE THE DROPDOWN MENU IN THE BLUE-SHADED COLUMN "I" TO INDICATE WHETHER THEY HAVE AN OBJECTION TO THE GRANTEE'S SELF-ASSESSMENT.
IF SO, PROPOSE A NEW TIMELINE FOR THE ACTION IMPLEMENTATION IN COLUMN "J" .
COLUMNS "I" AND "J"
COLUMN "H"
COLUMN "D"
INSTRUCTIONS FOR GLF REVIEWER
GRANTEES ENTER THE VERIFICATION MEANS IN THE BLUE-SHADED COLUMN “K”.
COLUMN "K"
COLUMNS "L" AND "M"
GLF REVIEWERS ENTER THEIR COMMENTS IN THE BLUE-SHADED COLUMN "L" AND “M”

## CHART
4 | Sum of Risk Probab
HIGH | 6
4 | 3
5 | 3
(blank)
(blank)
Grand Total | 6

## INTERNAL REFERENCES
1 MONTH | SMALL GRANT | 1Q | Biodiversity Management
2 MONTHS | MEDIUM GRANT | 2Q | Community - Occupational H&S
3 MONTHS | LARGE GRANT | 3Q | Waste Management
4 MONTHS | CATEGORY C | 4Q | Hazardous Material Management
5 MONTHS | CATEGORY B | 5Q | Integrated Pest Management
6 MONTHS | CATEGORY A | 6Q | Emergency Response
7 MONTHS | PS2 | 7Q | Process Framework
8 MONTHS | PS3 | 8Q | Livelihood Restoration
9 MONTHS | PS4 | 9Q | Security Management Plan
10 MONTHS | PS5 | 10Q | Free, Prior, and Informed Consent (protocol)
11 MONTHS | PS6 | 11Q | Human Rights Due Diligence
12 MONTHS | PS7 | 12Q | Other
13 MONTHS | PS8 | CLOSURE
14 MONTHS | MONTHLY | 5 | Immediately
15 MONTHS | QUARTERLY | 4 | Over the next month
16 MONTHS | SEMIANNUAL | 3 | Over the next quarter
17 MONTHS | YEARLY | 2 | Over the next six months
18 MONTHS | OTHER | 1 | When possible
19 MONTHS |  | R-01- | Other
20 MONTHS | YES | R-02- | Same Time Limit
21 MONTHS | NO | R-03- | According to the schedule
22 MONTHS | NOT YET APPLICABLE | R-04- | Earlier than the schedule
23 MONTHS | NOT YET APPLICABLE | R-05- | Slightly behind schedule
24 MONTHS | NO OBJECTIONS | R-06- | Severe delay
25 MONTHS | OBJECTIONS - SEE COMMENTS | R-07- | Other
26 MONTHS | OTHER - SEE COMMENTS | R-08-
27 MONTHS | NO COMMENTS | R-09-
28 MONTHS |  | R10-
29 MONTHS |  | R-11-
30 MONTHS |  | R-12-
31 MONTHS |  | R-13-
32 MONTHS |  | R-14-
33 MONTHS |  | R-15-
34 MONTHS |  | None
35 MONTHS |  | 1
36 MONTHS |  | 2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
More than 20

## DBHEADER (hidden)
Key | Requisite | Project ID | Date | Person | Title | Report Nr | Grant Category | Grant Type | Applicant | Risk Level | Frequency | Risk Probab | Risk Impact | Months | Progress | Execution Pct | Risk Category
2. GRIEVANCE MANR-05- | 2. GRIEVANCE MAN | 01-2025 | 2024-08-12 | John Lenon | YES MILANO | R-05- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | HIGH | 0 | 4 | 3 | 12 MONTHS | Slightly behind schedule | 0.33333 | 3
2. GRIEVANCE MANR-01- | 2. GRIEVANCE MAN | 01-2025 | 2024-08-12 | John Lenon | YES MILANO | R-01- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | MEDIUM | 0 | 2 | 3 | 12 MONTHS | Slightly behind schedule | 0.33333 | 2
3. SEPR-01- | 3. SEP | 01-2025 | 2024-03-22 | Louis Armstrong | YES MILANO | R-01- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | LOW | 0 | 1 | 2 | 1 MONTH | According to the schedule | 0.027778 | 1
3. SEPR-02- | 3. SEP | 01-2025 | 2024-11-22 | Louis Armstrong | YES MILANO | R-02- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | MEDIUM | 0 | 3 | 2 | 5 MONTHS | Slightly behind schedule | 0.13889 | 2
3. SEPR-03- | 3. SEP | 01-2025 | 2024-03-25 | Louis Armstrong | YES MILANO | R-03- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | MEDIUM | 0 | 3 | 3 | 6 MONTHS | Slightly behind schedule | 0.16667 | 2
3. SEPR-04- | 3. SEP | 01-2025 | 2024-03-25 | Louis Armstrong | YES MILANO | R-04- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | VERY HIGH | 0 | 5 | 4 | 9 MONTHS | Severe delay | 0.25 | 4
3. SEPR-05- | 3. SEP | 01-2025 | 2024-03-25 | Louis Armstrong | YES MILANO | R-05- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | VERY HIGH | 0 | 5 | 4 | 11 MONTHS | Slightly behind schedule | 0.30556 | 4
4. GENDERR-01- | 4. GENDER | 01-2025 | 2024-02-20 | Greta Garbo | YES MILANO | R-01- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | LOW | YEARLY | 1 | 1 | 2 MONTHS | Earlier than the schedule | 0.055556 | 1
4. GENDERR-02- | 4. GENDER | 01-2025 | 2024-02-20 | R. Bolaño | Input the name of the Project | R-02- | CATEGORY B | LARGE GRANT | Input the name of the Grantee | LOW | YEARLY | 2 | 2 | 6 MONTHS | Earlier than the schedule | 0.16667 | 1
4. GENDERR-03- | 4. GENDER | 01-2025 | 2024-02-20 | R. Bolaño | Input the name of the Project | R-03- | CATEGORY B | LARGE GRANT | Input the name of the Grantee | LOW | YEARLY | 2 | 2 | 6 MONTHS | Earlier than the schedule | 0.16667 | 1
4. GENDERR-04- | 4. GENDER | 01-2025 | 2024-02-20 | R. Bolaño | YES MILANO | R-04- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | HIGH | YEARLY | 4 | 3 | 12 MONTHS | Earlier than the schedule | 0.33333 | 3
4. GENDERR-05- | 4. GENDER | 01-2025 | 2024-02-20 | R. Bolaño | YES MILANO | R-05- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | LOW | YEARLY | 2 | 2 | 18 MONTHS | Earlier than the schedule | 0.5 | 1
4. GENDERR-06- | 4. GENDER | 01-2025 | 2024-02-20 | R. Bolaño | YES MILANO | R-06- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | LOW | YEARLY | 1 | 1 | 21 MONTHS | Earlier than the schedule | 0.58333 | 1
1. LABOURR-01- | 1. LABOUR | 01-2025 | 2024-08-25 | Another Reviewer | YES MILANO | R-01- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | LOW | QUARTERLY | 1 | 3 | 2 MONTHS | According to the schedule | 0.055556 | 1
1. LABOURR-02- | 1. LABOUR | 01-2025 | 2024-10-25 | Another Reviewer | YES MILANO | R-02- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | MEDIUM | QUARTERLY | 3 | 3 | 4 MONTHS | Slightly behind schedule | 0.11111 | 2
1. LABOURR-03- | 1. LABOUR | 01-2025 | 2024-12-25 | Another Reviewer | YES MILANO | R-03- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | HIGH | QUARTERLY | 4 | 3 | 6 MONTHS | Severe delay | 0.16667 | 3
1. LABOURR-04- | 1. LABOUR | 01-2025 | 2025-02-25 | Another Reviewer | YES MILANO | R-04- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | MEDIUM | QUARTERLY | 2 | 3 | 9 MONTHS | Slightly behind schedule | 0.25 | 2
1. LABOURR-05- | 1. LABOUR | 01-2025 | 2025-05-25 | Another Reviewer | YES MILANO | R-05- | CATEGORY C | SMALL GRANT | Juieta Rodriguez and partners | LOW | QUARTERLY | 1 | 2 | 12 MONTHS | According to the schedule | 0.33333 | 1
2. GRIEVANCE MANR-02- | 2. GRIEVANCE MAN | 01-2025 | 2024-08-12 | John Lenon | YES MILANO | R-02- | CATEGORY B | LARGE GRANT | Juieta Rodriguez and partners | MEDIUM | 0 | 3 | 2 | 12 MONTHS | Slightly behind schedule | 0.33333 | 2
3. SEPR-06- | 3. SEP | 01-2025 | 2024-03-25 | Louis Armstrong | YES MILANO | R-06- | CATEGORY B | LARGE GRANT | Juieta Rodriguez and partners | VERY HIGH | 0 | 5 | 4 | 11 MONTHS | Slightly behind schedule | 0.30556 | 4
3. SEPR-07- | 3. SEP | 01-2025 | 2024-03-25 | Louis Armstrong | Input the name of the Project | R-07- | CATEGORY B | LARGE GRANT | Input the name of the Grantee | LOW | QUARTERLY | 1 | 2 | 11 MONTHS | Slightly behind schedule | 0.30556 | 1
3. SEPR-08- | 3. SEP | 01-2025 | 2024-03-25 | Louis Armstrong | Input the name of the Project | R-08- | CATEGORY B | LARGE GRANT | Input the name of the Grantee | LOW | QUARTERLY | 1 | 2 | 11 MONTHS | Slightly behind schedule | 0.30556 | 1

## DBBODY (hidden)
Key | Requisite | Report Nr | Question Nr | EAS | Question | Answer | Action | Time Limit | GLF Review | New Time Limit | Verification | Grantee's Comm | GLF's Comm
2. GRIEVANCE MANR-05-A | 2. GRIEVANCE MAN | R-05- | A | 2.1 | Is there a functional grievance mechanism available to the community? | NO | Projects must have a Grievance Mechanism compatible with the GLF's mechanism, available to communities and other stakeholders. If the mechanism is not functional, it must be operational by the end of next quarter at the latest.
2. GRIEVANCE MANR-05-B | 2. GRIEVANCE MAN | R-05- | B | 2.2 | Is there a functional grievance mechanism available for project employees | YES | Projects must have a Grievance Mechanism compatible with the GLF mechanism, available to project workers. If the mechanism is not functional, it must be operational by the end of next quarter at the latest.
2. GRIEVANCE MANR-05-C | 2. GRIEVANCE MAN | R-05- | C | 2.3 | Does the organization respond to or escalate complaints on time? | YES | If the answer is NO, increase the risk level. Grantees have two options for addressing a grievance: 1) A simple grievance can be addressed through the "Quick Response to Simple Grievances" process. 2) If the grievance is more complex and requires an investigation, it must be escalated to the GLF. Grantees must take prompt action to address either type of grievance.
2. GRIEVANCE MANR-05-D | 2. GRIEVANCE MAN | R-05- | D | 2.4 | How many complaints were received in the reporting period? | NO | If no complaints were received during the reporting period, it may be because the grievance management mechanism is not fully accessible. Grantees must ensure the accessibility and usability of their mechanisms. Conversely, a high number of complaints may indicate significant project problems that Grantees need to address.
2. GRIEVANCE MANR-05-F | 2. GRIEVANCE MAN | R-05- | F | 2.5 | Has the grievance management ever received any complaints? | YES | If the answer is NO, it could indicate that grievance management is not functioning properly. It may be inaccessible or not adequately disseminated among stakeholders. Grantees must review all aspects of their mechanisms.
2. GRIEVANCE MANR-01-A | 2. GRIEVANCE MAN | R-01- | A | 2.1 | Is there a functional grievance mechanism available to the community? | YES | Projects must have a Grievance Mechanism compatible with the GLF's mechanism, available to communities and other stakeholders. If the mechanism is not functional, it must be operational by the end of next quarter at the latest.
2. GRIEVANCE MANR-01-B | 2. GRIEVANCE MAN | R-01- | B | 2.2 | Is there a functional grievance mechanism available for project employees | YES | Projects must have a Grievance Mechanism compatible with the GLF mechanism, available to project workers. If the mechanism is not functional, it must be operational by the end of next quarter at the latest.
2. GRIEVANCE MANR-01-C | 2. GRIEVANCE MAN | R-01- | C | 2.3 | Does the organization respond to or escalate complaints on time? | YES | If the answer is NO, increase the risk level. Grantees have two options for addressing a grievance: 1) A simple grievance can be addressed through the "Quick Response to Simple Grievances" process. 2) If the grievance is more complex and requires an investigation, it must be escalated to the GLF. Grantees must take prompt action to address either type of grievance.
2. GRIEVANCE MANR-01-D | 2. GRIEVANCE MAN | R-01- | D | 2.4 | How many complaints were received in the reporting period? | YES | If no complaints were received during the reporting period, it may be because the grievance management mechanism is not fully accessible. Grantees must ensure the accessibility and usability of their mechanisms. Conversely, a high number of complaints may indicate significant project problems that Grantees need to address.
2. GRIEVANCE MANR-01-F | 2. GRIEVANCE MAN | R-01- | F | 2.5 | Has the grievance management ever received any complaints? | YES | If the answer is NO, it could indicate that grievance management is not functioning properly. It may be inaccessible or not adequately disseminated among stakeholders. Grantees must review all aspects of their mechanisms.
3. SEPR-01-A | 3. SEP | R-01- | A | 5.1 | Has the Grantee reported any incidents or accidents on the project during the reporting period? | NOT YET APPLICABLE
3. SEPR-01-B | 3. SEP | R-01- | B | 5.2 | Has the Grantee reported the incident or accident to the relevant authorities in Galapagos? | YES | GLF requires Grantees to promptly report any event, incident or accident related to environmental, occupational health and safety, public health and safety, or social issues occurring in the project area that may have a significant adverse impact, attract negative external attention, or give rise to potential liability. If there is no explanation for the lack of a report, raise the risk level.
3. SEPR-01-D | 3. SEP | R-01- | D | 5.3 | Was the incident or accident report filed using the GLF reporting tool? | YES | The Grantee must report to GLF and to the appropriate regulatory agency on community and occupational health and safety matters in a manner that satisfies Ecuadorian legislation and the requirements set by following the EHS Guideline (2.0). The Grantee should use the the Occupational Accident / Incident Reporting Form of the GLF or a similar format.
3. SEPR-01-E | 3. SEP | R-01- | E | 5.4 | Has the incident or accident been investigated by someone who is knowledgeable and competent in occupational safety? | YES | All reported occupational accidents, diseases, dangerous occurrences, incidents, and near misses should be investigated by someone knowledgeable/competent in occupational safety. If the investigation has not been carried out without an acceptable reason, then the project's risk level should be increased.
3. SEPR-01-F | 3. SEP | R-01- | F | 5.6 | Has the Grantee implemented any preventive measures or improved processes as a result of the investigation? | NO | If the investigation has been completed and the root causes have been identified, the Grantee must take appropriate measures to prevent these accidents or incidents from happening again. Increase the project’s risk level until preventive measures are in place.
3. SEPR-01-G | 3. SEP | R-01- | G | 5.7 | Has the Grantee established processes and systems to report and record work-related accidents, diseases, dangerous occurrences, and incidents? | NO
3. SEPR-02-A | 3. SEP | R-02- | A | 5.1 | Has the Grantee reported any incidents or accidents on the project during the reporting period? | NOT YET APPLICABLE
3. SEPR-02-B | 3. SEP | R-02- | B | 5.2 | Has the Grantee reported the incident or accident to the relevant authorities in Galapagos? | YES | GLF requires Grantees to promptly report any event, incident or accident related to environmental, occupational health and safety, public health and safety, or social issues occurring in the project area that may have a significant adverse impact, attract negative external attention, or give rise to potential liability. If there is no explanation for the lack of a report, raise the risk level.
3. SEPR-02-D | 3. SEP | R-02- | D | 5.3 | Was the incident or accident report filed using the GLF reporting tool? | YES | The Grantee must report to GLF and to the appropriate regulatory agency on community and occupational health and safety matters in a manner that satisfies Ecuadorian legislation and the requirements set by following the EHS Guideline (2.0). The Grantee should use the the Occupational Accident / Incident Reporting Form of the GLF or a similar format.
3. SEPR-02-E | 3. SEP | R-02- | E | 5.4 | Has the incident or accident been investigated by someone who is knowledgeable and competent in occupational safety? | YES | All reported occupational accidents, diseases, dangerous occurrences, incidents, and near misses should be investigated by someone knowledgeable/competent in occupational safety. If the investigation has not been carried out without an acceptable reason, then the project's risk level should be increased.
3. SEPR-02-F | 3. SEP | R-02- | F | 5.6 | Has the Grantee implemented any preventive measures or improved processes as a result of the investigation? | NO | If the investigation has been completed and the root causes have been identified, the Grantee must take appropriate measures to prevent these accidents or incidents from happening again. Increase the project’s risk level until preventive measures are in place.
3. SEPR-02-G | 3. SEP | R-02- | G | 5.7 | Has the Grantee established processes and systems to report and record work-related accidents, diseases, dangerous occurrences, and incidents? | NO
3. SEPR-03-A | 3. SEP | R-03- | A | 3.1 | Does the project have a SEP? | NOT YET APPLICABLE | All projects must have a Stakeholder Engagement Plan (SEP) formulated in accordance with the ESMP.
3. SEPR-03-B | 3. SEP | R-03- | B | 3.2 | Is the grantee effectively engaging with project stakeholders? | YES | Consider increasing the risk level. Effective stakeholder engagement is crucial for achieving project results and maintaining good environmental and social performance. Grantees must ensure ongoing engagement with project stakeholders.
3. SEPR-03-D | 3. SEP | R-03- | D | 3.3 | Have the stakeholder engagement activities been conducted as scheduled during the period being monitored? | YES | Consider increasing the risk level, unless there is a satisfactory explanation. Grantees should strive to carry out their stakeholder activities as planned unless there are emergent issues that require changes.
3. SEPR-03-E | 3. SEP | R-03- | E | 3.4 | Are there any concerns raised by stakeholders that could significantly impact the project? | YES | If stakeholders have serious concerns about the project, the Grantee should respond to these concerns and most likely advance concrete actions related to the concerns.
3. SEPR-03-F | 3. SEP | R-03- | F | 3.5 | Is there equal participation between men and women in stakeholder activities, or is either group overrepresented to the detriment of the other? | NO | The Grantee must make a significant effort to ensure equitable participation unless there is a clear reason for a substantial difference in participation between the two groups.
3. SEPR-03-G | 3. SEP | R-03- | G | 3.6 | Is the Grantee correctly documenting stakeholder engagement activities? | NO | The Grantee must accurately record stakeholder involvement activities using various media, such as written, audiovisual, or other forms of media.
3. SEPR-04-A | 3. SEP | R-04- | A | 3.1 | Does the project have a SEP? | NOT YET APPLICABLE | All projects must have a Stakeholder Engagement Plan (SEP) formulated in accordance with the ESMP.
3. SEPR-04-B | 3. SEP | R-04- | B | 3.2 | Is the grantee effectively engaging with project stakeholders? | YES | Consider increasing the risk level. Effective stakeholder engagement is crucial for achieving project results and maintaining good environmental and social performance. Grantees must ensure ongoing engagement with project stakeholders.
3. SEPR-04-D | 3. SEP | R-04- | D | 3.3 | Have the stakeholder engagement activities been conducted as scheduled during the period being monitored? | YES | Consider increasing the risk level, unless there is a satisfactory explanation. Grantees should strive to carry out their stakeholder activities as planned unless there are emergent issues that require changes.
3. SEPR-04-E | 3. SEP | R-04- | E | 3.4 | Are there any concerns raised by stakeholders that could significantly impact the project? | YES | If stakeholders have serious concerns about the project, the Grantee should respond to these concerns and most likely advance concrete actions related to the concerns.
3. SEPR-04-F | 3. SEP | R-04- | F | 3.5 | Is there equal participation between men and women in stakeholder activities, or is either group overrepresented to the detriment of the other? | NO | The Grantee must make a significant effort to ensure equitable participation unless there is a clear reason for a substantial difference in participation between the two groups.
3. SEPR-04-G | 3. SEP | R-04- | G | 3.6 | Is the Grantee correctly documenting stakeholder engagement activities? | NO | The Grantee must accurately record stakeholder involvement activities using various media, such as written, audiovisual, or other forms of media.
3. SEPR-05-A | 3. SEP | R-05- | A | 3.1 | Does the project have a SEP? | NOT YET APPLICABLE | All projects must have a Stakeholder Engagement Plan (SEP) formulated in accordance with the ESMP.
3. SEPR-05-B | 3. SEP | R-05- | B | 3.2 | Is the grantee effectively engaging with project stakeholders? | YES | Consider increasing the risk level. Effective stakeholder engagement is crucial for achieving project results and maintaining good environmental and social performance. Grantees must ensure ongoing engagement with project stakeholders.
3. SEPR-05-D | 3. SEP | R-05- | D | 3.3 | Have the stakeholder engagement activities been conducted as scheduled during the period being monitored? | YES | Consider increasing the risk level, unless there is a satisfactory explanation. Grantees should strive to carry out their stakeholder activities as planned unless there are emergent issues that require changes.
3. SEPR-05-E | 3. SEP | R-05- | E | 3.4 | Are there any concerns raised by stakeholders that could significantly impact the project? | YES | If stakeholders have serious concerns about the project, the Grantee should respond to these concerns and most likely advance concrete actions related to the concerns.
3. SEPR-05-F | 3. SEP | R-05- | F | 3.5 | Is there equal participation between men and women in stakeholder activities, or is either group overrepresented to the detriment of the other? | NO | The Grantee must make a significant effort to ensure equitable participation unless there is a clear reason for a substantial difference in participation between the two groups.
3. SEPR-05-G | 3. SEP | R-05- | G | 3.6 | Is the Grantee correctly documenting stakeholder engagement activities? | NO | The Grantee must accurately record stakeholder involvement activities using various media, such as written, audiovisual, or other forms of media.
4. GENDERR-02-A | 4. GENDER | R-02- | A | 4.1 | Is the project taking into account relevant gender issues and concerns? | YES
4. GENDERR-02-B | 4. GENDER | R-02- | B | 4.2 | Are the project indicators, milestones, and targets inclusive of gender considerations? | NO
4. GENDERR-02-D | 4. GENDER | R-02- | D | 4.4 | Are the project activities conflicting with the GLF's gender equality plan in any way?
4. GENDERR-02-I | 4. GENDER | R-02- | I | 4.6 | Does the project progress report include the intervention's impact on women, men, and gender relations? | YES
4. GENDERR-03-A | 4. GENDER | R-03- | A | 4.1 | Is the project taking into account relevant gender issues and concerns? | YES
4. GENDERR-03-B | 4. GENDER | R-03- | B | 4.2 | Are the project indicators, milestones, and targets inclusive of gender considerations? | NO
4. GENDERR-03-D | 4. GENDER | R-03- | D | 4.4 | Are the project activities conflicting with the GLF's gender equality plan in any way?
4. GENDERR-03-I | 4. GENDER | R-03- | I | 4.6 | Does the project progress report include the intervention's impact on women, men, and gender relations? | YES
4. GENDERR-04-A | 4. GENDER | R-04- | A | 4.1 | Is the project taking into account relevant gender issues and concerns? | NO
4. GENDERR-04-B | 4. GENDER | R-04- | B | 4.2 | Are the project indicators, milestones, and targets inclusive of gender considerations? | NO
4. GENDERR-04-D | 4. GENDER | R-04- | D | 4.3 | Does the project collect sex-disaggregated data? | NO
4. GENDERR-04-I | 4. GENDER | R-04- | I | 4.6 | Does the project progress report include the intervention's impact on women, men, and gender relations? | YES
4. GENDERR-05-A | 4. GENDER | R-05- | A | 4.1 | Is the project taking into account relevant gender issues and concerns? | YES
4. GENDERR-05-B | 4. GENDER | R-05- | B | 4.2 | Are the project indicators, milestones, and targets inclusive of gender considerations? | YES
4. GENDERR-05-D | 4. GENDER | R-05- | D | 4.3 | Does the project collect sex-disaggregated data? | YES
4. GENDERR-05-I | 4. GENDER | R-05- | I | 4.6 | Does the project progress report include the intervention's impact on women, men, and gender relations? | NO
4. GENDERR-06-A | 4. GENDER | R-06- | A | 4.1 | Is the project taking into account relevant gender issues and concerns? | YES
4. GENDERR-06-B | 4. GENDER | R-06- | B | 4.2 | Are the project indicators, milestones, and targets inclusive of gender considerations? | YES
4. GENDERR-06-D | 4. GENDER | R-06- | D | 4.3 | Does the project collect sex-disaggregated data? | YES
4. GENDERR-06-I | 4. GENDER | R-06- | I | 4.6 | Does the project progress report include the intervention's impact on women, men, and gender relations? | YES
1. LABOURR-01-A | 1. LABOUR | R-01- | A | 1.1 | Is there a clear and transparent hiring process for project staff? | YES | The grantee must ensure a clear and transparent hiring process to fulfill their Labor and Working Conditions. The risk level should be increased, and the grantee should implement this transparent process immediately. | When possible | OBJECTIONS - SEE COMMENTS | Immediately
1. LABOURR-01-B | 1. LABOUR | R-01- | B | 1.2 | Do the project employees have sufficient documentation about their working conditions and rights, including employment contracts, work schedules, salaries, overtime, compensation, and social or legal benefits? | NOT YET APPLICABLE | The grantee must provide adequate documentation to all staff and provide evidence of this action to GLF.
1. LABOURR-01-D | 1. LABOUR | R-01- | D | 1.3 | Does the project ensure that there is no discrimination based on sex, sexual orientation, age, ethnicity, disability, or any other factor and that work of equal value corresponds to equal pay? | YES | The grantee must ensure equal remuneration for work of equal value, without discrimination. The risk level should be increased, and the grantee should implement this principle immediately. | When possible | OBJECTIONS - SEE COMMENTS | Immediately
1. LABOURR-01-E | 1. LABOUR | R-01- | E | 1.4 | Is a functional Grievance Management Mechanism available for people working on the project? | NO | A functional Grievance Management Mechanism available for project workers is part of the grantee’s commitment to Labour and Working Conditions. It should be put in place as soon as possible, and in the meantime, the risk level should be increased. | Over the next quarter | NO OBJECTIONS | Over the next quarter
1. LABOURR-01-F | 1. LABOUR | R-01- | F | 1.5 | Are the workers on the project at risk of occupational hazards? | YES | If workers are exposed to occupational hazards, the grantee must develop an Occupational Health and Safety Plan. The risk level must be increased until this plan is implemented.
1. LABOURR-01-G | 1. LABOUR | R-01- | G | 1.6 | Have there been cases of Sexual and Gender Violence (SGBV) among the people employed by the project during the period under monitoring? | NO | GLF is committed to preventing SGBV and mitigating its negative impacts. If the answer is YES, the grantee must report the actions taken and the outcome of this case. The risk level must be increased until preventive measures are fully implemented to avoid such cases in the future.
1. LABOURR-01-H | 1. LABOUR | R-01- | H | 1.7 | Does any aspect of the project execution contradict the Grantee's Statement of Compliance with Labour and Working Conditions? | YES | The grantee is responsible for ensuring that the Labor and Working Conditions outlined in the ESMP and grant agreement are met. The risk level must be raised until corrective measures are in place and these conditions are met.
1. LABOURR-01-I | 1. LABOUR | R-01- | I | 1.8 | Overall, is there a high risk of causing harm to communities or the environment with the activity or project that has been monitored? | NO | The grantee must take immediate action to prevent harm, increase the risk level, and report to GLF on the actions taken.
4. GENDERR-01-A | 4. GENDER | R-01- | A | 4.1 | Is the project taking into account relevant gender issues and concerns? | YES
4. GENDERR-01-B | 4. GENDER | R-01- | B | 4.2 | Are the project indicators, milestones, and targets inclusive of gender considerations? | YES
4. GENDERR-01-D | 4. GENDER | R-01- | D | 4.3 | Does the project collect sex-disaggregated data? | YES
4. GENDERR-01-I | 4. GENDER | R-01- | I | 4.6 | Does the project progress report include the intervention's impact on women, men, and gender relations? | YES
1. LABOURR-02-A | 1. LABOUR | R-02- | A | 1.1 | Is there a clear and transparent hiring process for project staff? | YES | The grantee must ensure a clear and transparent hiring process to fulfill their Labor and Working Conditions. The risk level should be increased, and the grantee should implement this transparent process immediately. | When possible | OBJECTIONS - SEE COMMENTS | Immediately
1. LABOURR-02-B | 1. LABOUR | R-02- | B | 1.2 | Do the project employees have sufficient documentation about their working conditions and rights, including employment contracts, work schedules, salaries, overtime, compensation, and social or legal benefits? | NOT YET APPLICABLE | The grantee must provide adequate documentation to all staff and provide evidence of this action to GLF.
1. LABOURR-02-D | 1. LABOUR | R-02- | D | 1.3 | Does the project ensure that there is no discrimination based on sex, sexual orientation, age, ethnicity, disability, or any other factor and that work of equal value corresponds to equal pay? | YES | The grantee must ensure equal remuneration for work of equal value, without discrimination. The risk level should be increased, and the grantee should implement this principle immediately. | When possible | OBJECTIONS - SEE COMMENTS | Immediately
1. LABOURR-02-E | 1. LABOUR | R-02- | E | 1.4 | Is a functional Grievance Management Mechanism available for people working on the project? | NO | A functional Grievance Management Mechanism available for project workers is part of the grantee’s commitment to Labour and Working Conditions. It should be put in place as soon as possible, and in the meantime, the risk level should be increased. | Over the next quarter | NO OBJECTIONS | Over the next quarter
1. LABOURR-02-F | 1. LABOUR | R-02- | F | 1.5 | Are the workers on the project at risk of occupational hazards? | YES | If workers are exposed to occupational hazards, the grantee must develop an Occupational Health and Safety Plan. The risk level must be increased until this plan is implemented.
1. LABOURR-02-G | 1. LABOUR | R-02- | G | 1.6 | Have there been cases of Sexual and Gender Violence (SGBV) among the people employed by the project during the period under monitoring? | NO | GLF is committed to preventing SGBV and mitigating its negative impacts. If the answer is YES, the grantee must report the actions taken and the outcome of this case. The risk level must be increased until preventive measures are fully implemented to avoid such cases in the future.
1. LABOURR-02-H | 1. LABOUR | R-02- | H | 1.7 | Does any aspect of the project execution contradict the Grantee's Statement of Compliance with Labour and Working Conditions? | YES | The grantee is responsible for ensuring that the Labor and Working Conditions outlined in the ESMP and grant agreement are met. The risk level must be raised until corrective measures are in place and these conditions are met.
1. LABOURR-02-I | 1. LABOUR | R-02- | I | 1.8 | Overall, is there a high risk of causing harm to communities or the environment with the activity or project that has been monitored? | NO | The grantee must take immediate action to prevent harm, increase the risk level, and report to GLF on the actions taken.
1. LABOURR-03-A | 1. LABOUR | R-03- | A | 1.1 | Is there a clear and transparent hiring process for project staff? | YES | The grantee must ensure a clear and transparent hiring process to fulfill their Labor and Working Conditions. The risk level should be increased, and the grantee should implement this transparent process immediately. | When possible | OBJECTIONS - SEE COMMENTS | Immediately
1. LABOURR-03-B | 1. LABOUR | R-03- | B | 1.2 | Do the project employees have sufficient documentation about their working conditions and rights, including employment contracts, work schedules, salaries, overtime, compensation, and social or legal benefits? | NOT YET APPLICABLE | The grantee must provide adequate documentation to all staff and provide evidence of this action to GLF.
1. LABOURR-03-D | 1. LABOUR | R-03- | D | 1.3 | Does the project ensure that there is no discrimination based on sex, sexual orientation, age, ethnicity, disability, or any other factor and that work of equal value corresponds to equal pay? | YES | The grantee must ensure equal remuneration for work of equal value, without discrimination. The risk level should be increased, and the grantee should implement this principle immediately. | When possible | OBJECTIONS - SEE COMMENTS | Immediately
1. LABOURR-03-E | 1. LABOUR | R-03- | E | 1.4 | Is a functional Grievance Management Mechanism available for people working on the project? | NO | A functional Grievance Management Mechanism available for project workers is part of the grantee’s commitment to Labour and Working Conditions. It should be put in place as soon as possible, and in the meantime, the risk level should be increased. | Over the next quarter | NO OBJECTIONS | Over the next quarter
1. LABOURR-03-F | 1. LABOUR | R-03- | F | 1.5 | Are the workers on the project at risk of occupational hazards? | YES | If workers are exposed to occupational hazards, the grantee must develop an Occupational Health and Safety Plan. The risk level must be increased until this plan is implemented.
1. LABOURR-03-G | 1. LABOUR | R-03- | G | 1.6 | Have there been cases of Sexual and Gender Violence (SGBV) among the people employed by the project during the period under monitoring? | NO | GLF is committed to preventing SGBV and mitigating its negative impacts. If the answer is YES, the grantee must report the actions taken and the outcome of this case. The risk level must be increased until preventive measures are fully implemented to avoid such cases in the future.
1. LABOURR-03-H | 1. LABOUR | R-03- | H | 1.7 | Does any aspect of the project execution contradict the Grantee's Statement of Compliance with Labour and Working Conditions? | YES | The grantee is responsible for ensuring that the Labor and Working Conditions outlined in the ESMP and grant agreement are met. The risk level must be raised until corrective measures are in place and these conditions are met.
1. LABOURR-03-I | 1. LABOUR | R-03- | I | 1.8 | Overall, is there a high risk of causing harm to communities or the environment with the activity or project that has been monitored? | NO | The grantee must take immediate action to prevent harm, increase the risk level, and report to GLF on the actions taken.
1. LABOURR-04-A | 1. LABOUR | R-04- | A | 1.1 | Is there a clear and transparent hiring process for project staff? | YES | The grantee must ensure a clear and transparent hiring process to fulfill their Labor and Working Conditions. The risk level should be increased, and the grantee should implement this transparent process immediately. | When possible | OBJECTIONS - SEE COMMENTS | Immediately
1. LABOURR-04-B | 1. LABOUR | R-04- | B | 1.2 | Do the project employees have sufficient documentation about their working conditions and rights, including employment contracts, work schedules, salaries, overtime, compensation, and social or legal benefits? | NOT YET APPLICABLE | The grantee must provide adequate documentation to all staff and provide evidence of this action to GLF.
1. LABOURR-04-D | 1. LABOUR | R-04- | D | 1.3 | Does the project ensure that there is no discrimination based on sex, sexual orientation, age, ethnicity, disability, or any other factor and that work of equal value corresponds to equal pay? | YES | The grantee must ensure equal remuneration for work of equal value, without discrimination. The risk level should be increased, and the grantee should implement this principle immediately. | When possible | OBJECTIONS - SEE COMMENTS | Immediately
1. LABOURR-04-E | 1. LABOUR | R-04- | E | 1.4 | Is a functional Grievance Management Mechanism available for people working on the project? | NO | A functional Grievance Management Mechanism available for project workers is part of the grantee’s commitment to Labour and Working Conditions. It should be put in place as soon as possible, and in the meantime, the risk level should be increased. | Over the next quarter | NO OBJECTIONS | Over the next quarter
1. LABOURR-04-F | 1. LABOUR | R-04- | F | 1.5 | Are the workers on the project at risk of occupational hazards? | YES | If workers are exposed to occupational hazards, the grantee must develop an Occupational Health and Safety Plan. The risk level must be increased until this plan is implemented.
1. LABOURR-04-G | 1. LABOUR | R-04- | G | 1.6 | Have there been cases of Sexual and Gender Violence (SGBV) among the people employed by the project during the period under monitoring? | NO | GLF is committed to preventing SGBV and mitigating its negative impacts. If the answer is YES, the grantee must report the actions taken and the outcome of this case. The risk level must be increased until preventive measures are fully implemented to avoid such cases in the future.
1. LABOURR-04-H | 1. LABOUR | R-04- | H | 1.7 | Does any aspect of the project execution contradict the Grantee's Statement of Compliance with Labour and Working Conditions? | YES | The grantee is responsible for ensuring that the Labor and Working Conditions outlined in the ESMP and grant agreement are met. The risk level must be raised until corrective measures are in place and these conditions are met.
1. LABOURR-04-I | 1. LABOUR | R-04- | I | 1.8 | Overall, is there a high risk of causing harm to communities or the environment with the activity or project that has been monitored? | NO | The grantee must take immediate action to prevent harm, increase the risk level, and report to GLF on the actions taken.
1. LABOURR-05-A | 1. LABOUR | R-05- | A | 1.1 | Is there a clear and transparent hiring process for project staff? | YES | The grantee must ensure a clear and transparent hiring process to fulfill their Labor and Working Conditions. The risk level should be increased, and the grantee should implement this transparent process immediately. | When possible | OBJECTIONS - SEE COMMENTS | Immediately
1. LABOURR-05-B | 1. LABOUR | R-05- | B | 1.2 | Do the project employees have sufficient documentation about their working conditions and rights, including employment contracts, work schedules, salaries, overtime, compensation, and social or legal benefits? | NOT YET APPLICABLE | The grantee must provide adequate documentation to all staff and provide evidence of this action to GLF.
1. LABOURR-05-D | 1. LABOUR | R-05- | D | 1.3 | Does the project ensure that there is no discrimination based on sex, sexual orientation, age, ethnicity, disability, or any other factor and that work of equal value corresponds to equal pay? | YES | The grantee must ensure equal remuneration for work of equal value, without discrimination. The risk level should be increased, and the grantee should implement this principle immediately. | When possible | OBJECTIONS - SEE COMMENTS | Immediately
1. LABOURR-05-E | 1. LABOUR | R-05- | E | 1.4 | Is a functional Grievance Management Mechanism available for people working on the project? | NO | A functional Grievance Management Mechanism available for project workers is part of the grantee’s commitment to Labour and Working Conditions. It should be put in place as soon as possible, and in the meantime, the risk level should be increased. | Over the next quarter | NO OBJECTIONS | Over the next quarter
1. LABOURR-05-F | 1. LABOUR | R-05- | F | 1.5 | Are the workers on the project at risk of occupational hazards? | YES | If workers are exposed to occupational hazards, the grantee must develop an Occupational Health and Safety Plan. The risk level must be increased until this plan is implemented.
1. LABOURR-05-G | 1. LABOUR | R-05- | G | 1.6 | Have there been cases of Sexual and Gender Violence (SGBV) among the people employed by the project during the period under monitoring? | NO | GLF is committed to preventing SGBV and mitigating its negative impacts. If the answer is YES, the grantee must report the actions taken and the outcome of this case. The risk level must be increased until preventive measures are fully implemented to avoid such cases in the future.
1. LABOURR-05-H | 1. LABOUR | R-05- | H | 1.7 | Does any aspect of the project execution contradict the Grantee's Statement of Compliance with Labour and Working Conditions? | YES | The grantee is responsible for ensuring that the Labor and Working Conditions outlined in the ESMP and grant agreement are met. The risk level must be raised until corrective measures are in place and these conditions are met.
1. LABOURR-05-I | 1. LABOUR | R-05- | I | 1.8 | Overall, is there a high risk of causing harm to communities or the environment with the activity or project that has been monitored? | NO | The grantee must take immediate action to prevent harm, increase the risk level, and report to GLF on the actions taken.
2. GRIEVANCE MANR-02-A | 2. GRIEVANCE MAN | R-02- | A | 2.1 | Is there a functional grievance mechanism available to the community? | NO | Projects must have a Grievance Mechanism compatible with the GLF's mechanism, available to communities and other stakeholders. If the mechanism is not functional, it must be operational by the end of next quarter at the latest.
2. GRIEVANCE MANR-02-B | 2. GRIEVANCE MAN | R-02- | B | 2.2 | Is there a functional grievance mechanism available for project employees | YES | Projects must have a Grievance Mechanism compatible with the GLF mechanism, available to project workers. If the mechanism is not functional, it must be operational by the end of next quarter at the latest.
2. GRIEVANCE MANR-02-C | 2. GRIEVANCE MAN | R-02- | C | 2.3 | Does the organization respond to or escalate complaints on time? | YES | If the answer is NO, increase the risk level. Grantees have two options for addressing a grievance: 1) A simple grievance can be addressed through the "Quick Response to Simple Grievances" process. 2) If the grievance is more complex and requires an investigation, it must be escalated to the GLF. Grantees must take prompt action to address either type of grievance.
2. GRIEVANCE MANR-02-D | 2. GRIEVANCE MAN | R-02- | D | 2.4 | How many complaints were received in the reporting period? | NO | If no complaints were received during the reporting period, it may be because the grievance management mechanism is not fully accessible. Grantees must ensure the accessibility and usability of their mechanisms. Conversely, a high number of complaints may indicate significant project problems that Grantees need to address.
2. GRIEVANCE MANR-02-F | 2. GRIEVANCE MAN | R-02- | F | 2.5 | Has the grievance management ever received any complaints? | YES | If the answer is NO, it could indicate that grievance management is not functioning properly. It may be inaccessible or not adequately disseminated among stakeholders. Grantees must review all aspects of their mechanisms.
3. SEPR-06-A | 3. SEP | R-06- | A | 3.1 | Does the project have a SEP? | NOT YET APPLICABLE | All projects must have a Stakeholder Engagement Plan (SEP) formulated in accordance with the ESMP.
3. SEPR-06-B | 3. SEP | R-06- | B | 3.2 | Is the grantee effectively engaging with project stakeholders? | YES | Consider increasing the risk level. Effective stakeholder engagement is crucial for achieving project results and maintaining good environmental and social performance. Grantees must ensure ongoing engagement with project stakeholders.
3. SEPR-06-D | 3. SEP | R-06- | D | 3.3 | Have the stakeholder engagement activities been conducted as scheduled during the period being monitored? | YES | Consider increasing the risk level, unless there is a satisfactory explanation. Grantees should strive to carry out their stakeholder activities as planned unless there are emergent issues that require changes.
3. SEPR-06-E | 3. SEP | R-06- | E | 3.4 | Are there any concerns raised by stakeholders that could significantly impact the project? | YES | If stakeholders have serious concerns about the project, the Grantee should respond to these concerns and most likely advance concrete actions related to the concerns.
3. SEPR-06-F | 3. SEP | R-06- | F | 3.5 | Is there equal participation between men and women in stakeholder activities, or is either group overrepresented to the detriment of the other? | NO | The Grantee must make a significant effort to ensure equitable participation unless there is a clear reason for a substantial difference in participation between the two groups.
3. SEPR-06-G | 3. SEP | R-06- | G | 3.6 | Is the Grantee correctly documenting stakeholder engagement activities? | NO | The Grantee must accurately record stakeholder involvement activities using various media, such as written, audiovisual, or other forms of media.
3. SEPR-07-A | 3. SEP | R-07- | A | 3.1 | Does the project have a SEP? |  | All projects must have a Stakeholder Engagement Plan (SEP) formulated in accordance with the ESMP.
3. SEPR-07-B | 3. SEP | R-07- | B | 3.2 | Is the grantee effectively engaging with project stakeholders? |  | Consider increasing the risk level. Effective stakeholder engagement is crucial for achieving project results and maintaining good environmental and social performance. Grantees must ensure ongoing engagement with project stakeholders.
3. SEPR-07-D | 3. SEP | R-07- | D | 3.3 | Have the stakeholder engagement activities been conducted as scheduled during the period being monitored? |  | Consider increasing the risk level, unless there is a satisfactory explanation. Grantees should strive to carry out their stakeholder activities as planned unless there are emergent issues that require changes.
3. SEPR-07-E | 3. SEP | R-07- | E | 3.4 | Are there any concerns raised by stakeholders that could significantly impact the project? |  | If stakeholders have serious concerns about the project, the Grantee should respond to these concerns and most likely advance concrete actions related to the concerns.
3. SEPR-07-F | 3. SEP | R-07- | F | 3.5 | Is there equal participation between men and women in stakeholder activities, or is either group overrepresented to the detriment of the other? |  | The Grantee must make a significant effort to ensure equitable participation unless there is a clear reason for a substantial difference in participation between the two groups.
3. SEPR-07-G | 3. SEP | R-07- | G | 3.6 | Is the Grantee correctly documenting stakeholder engagement activities? |  | The Grantee must accurately record stakeholder involvement activities using various media, such as written, audiovisual, or other forms of media.
3. SEPR-08-A | 3. SEP | R-08- | A | 3.1 | Does the project have a SEP? |  | All projects must have a Stakeholder Engagement Plan (SEP) formulated in accordance with the ESMP.
3. SEPR-08-B | 3. SEP | R-08- | B | 3.2 | Is the grantee effectively engaging with project stakeholders? |  | Consider increasing the risk level. Effective stakeholder engagement is crucial for achieving project results and maintaining good environmental and social performance. Grantees must ensure ongoing engagement with project stakeholders.
3. SEPR-08-D | 3. SEP | R-08- | D | 3.3 | Have the stakeholder engagement activities been conducted as scheduled during the period being monitored? |  | Consider increasing the risk level, unless there is a satisfactory explanation. Grantees should strive to carry out their stakeholder activities as planned unless there are emergent issues that require changes.
3. SEPR-08-E | 3. SEP | R-08- | E | 3.4 | Are there any concerns raised by stakeholders that could significantly impact the project? |  | If stakeholders have serious concerns about the project, the Grantee should respond to these concerns and most likely advance concrete actions related to the concerns.
3. SEPR-08-F | 3. SEP | R-08- | F | 3.5 | Is there equal participation between men and women in stakeholder activities, or is either group overrepresented to the detriment of the other? |  | The Grantee must make a significant effort to ensure equitable participation unless there is a clear reason for a substantial difference in participation between the two groups.
3. SEPR-08-G | 3. SEP | R-08- | G | 3.6 | Is the Grantee correctly documenting stakeholder engagement activities? |  | The Grantee must accurately record stakeholder involvement activities using various media, such as written, audiovisual, or other forms of media.
4. GENDERR-02-C | 4. GENDER | R-02- | C | 4.3 | Does the project collect sex-disaggregated data?
4. GENDERR-02-E | 4. GENDER | R-02- | E | 4.5 | Has there been any case of gender-based violence reported during this period?
4. GENDERR-02-F | 4. GENDER | R-02- | F | 4.6 | Does the project progress report include the intervention's impact on women, men, and gender relations?
4. GENDERR-03-C | 4. GENDER | R-03- | C | 4.3 | Does the project collect sex-disaggregated data?
4. GENDERR-03-E | 4. GENDER | R-03- | E | 4.5 | Has there been any case of gender-based violence reported during this period?
4. GENDERR-03-F | 4. GENDER | R-03- | F | 4.6 | Does the project progress report include the intervention's impact on women, men, and gender relations?